## Project Description
PLEASE FILL IN THE BLUE HIGHLIGHTED CELLS USE TABS BELOW TO SWITCH BETWEEN WORKSHEETS |  |  | July 1, 2007 - June 30, 2008
1. PROJECT AUTHOR
a) | Author Name: | Jim Cahow
b) | Region: | NOR
c) | Telephone: | 715-637-6863
d) | Program: | wt
e) | Supervisor's Name: | Kathy Bartilson
2. PROJECT CATEGORY (1, 2a, 2b, 2c, 3a, 3b, 3c) |  | 1 or 2c
3. ACTIVITY CODE |  | WTSK
4. WORKPLAN DETAILS
a) | Project Description: | Chetek River & Chetek Chain of Lakes Diurnal DO and problematic algae bloom monitoring - Impaired Waters Monitoring
b) | Project Justification:
| 1.Why is project necessary? | Continue data collection from approved 2006 project
| 2. What mgmt. Question is being addressed? | During peak algae bloom and macrophyte senescence periods on the Chetek Chain of Lakes (July 15th-August 30th) assess what proportion of the total nutrient and sediment loadings to the upper Red Cedar River are coming from land uses in the upper Red Cedar River above the confluence with the Chetek River when compared to those nutrient and sediment loadings or additions coming from the Chetek River during August when peak Algae blooms and macrophyte senecence on the Chetek Chain of Lakes are believed to be a dominant source in the upper Red Cedar River Basin. Also conduct Diurnal D.O. Monitoring in the Chetek River to determine if fishery resources are being threatend by impairments related to excess algae production and macrophyte senescence within the Chetek Chain of Lakes that provides the source water for the Chetek River. We haven't as of yet done any targeted monitoring during this period to document the severity and duration of blooms on the Chetek Chain of Lakes and the presence or absence of toxic bluegreen algae species. This should be added to the project to bolster data that was summarized in Barr Eng 1999 report. These costs should be added into the project if the monitoring committe approves. The public outcry for monitoring to document the severity of the problem is considerable and the local public demands that are being voiced to local staff for an active managment solution that begins to recognize the severity of the problem and begins to pursue active management of all controlable problem sources of nutrients and sediments for the Chetek Chain of Lakes must be recognized and elevated to a higher level to gain adequate support and funding to rectify the impaired status. TMDL seems to be the obvious tool to move this forward.
c) | Locational Information:
| 1. Watershed | Chetek Chain of Lakes and Chetek River
| 2. County(ies) | Barron
| 3. Water Body(ies) - List All | Chetek River and Red Cedar River
| 3. WBIC(s) - List All | 2089000 & 2063500
d) | Performance Measures:
| 1. # of sample sites | A single site on the Chetek River at 4 1/2 Ave - two more sites should be collected on the Red Cedar River above and below the confluence to provide background info (6th Ave & CTH A&I Bridges). If sampling on the Chain of Lakes was added to the project a single site for each of the 5 lakes should be added.
| 2. # of of sampling events. | Up to 3 sampling events on the 3 river sites; depending on algae bloom & macrophyte senecence conditions and lab related sample time constraints (samples must be collected on Monday through Wednesday to avoid holding time exceedences). If the Chain of Lakes is added another 3 sampling events would be needed for the 5 lake sites.
| 3. Date sample collection complete. | August 30th, 2007
| 4. Date of complete data entry. | 2008-02-01
| 5. Date of final report. | This is a longterm project that seeks to characterize severity and duration of algae blooms during macrophyte senecense on the Chetek Chain of Lakes and the resulting impacts on the Chetek River which is depedent upon the Chain of Lakes for its source water. Sampling should continue until sample size is adequate to account for variability between samples and provide a crude measure of existing conditions. Final Report will be in 2008/2009.
e) | Data Management
| 1. What database will be used? | Existing DNR databases (SWIMS)
| 2. Who is responsible for entering data? | Jim cahow will insure that the data gets to the approriate people to be entered - ideally my year round LTE tech.
5. BUDGET
a) | FTE Hours Needed | Up to 40 hours for peak algae bloom & macrophyte senescence water chemistry samples on the Chetek River, Up to 40 hours for peak algae bloom & macrophyte senescence water chemistry samples on the Chetek Chain of Lakes, up to 120 hours for sonde familiarization, set up, and recovery, and data management. A summary report will require another 60 hours of FTE time.
b) | LTE Funds Needed | Equipment familiarity - 60 hours, sonde deployment& recovery - 120 hours, database training - 40 hours, data entry & management - 40 hours, report prep - 40 hours, assist with algae bloom/ macrophyte senecense samples for the Chetek River and background Red Cedar River sites- 40 hours Algae bloom sampling on the Chain of Lakes is another 40 hours of LTE
c) | Supplies - Describe in detail. | waders-$80,
d) | Travel | 5 weeks sonde placement, recovery, and maintenance = 750 miles & up to 3 weekly water chemistry samples documenting peak algae bloom and & Macrophyte senescence concnetrations on the Chetek River and the Chetek Chain of Lakes= 750 miles
e) | Contractual - Who? What? How Much?
f) | Equipment - What is needed and why? Cost? | Two additional data sondes at approximately $4,000 would help replace old failing equipment and help document loading differences between sites above and below Rice Lake on the upper Red Cedar River
g) | Capital Equipment >$5,000 - What is needed and why? Cost? | USGS gauging station request - $15,000
h) | State Lab of Hygiene Analyses - Describe the number and type of parameters being tested. | 3 weekly sampling events (July 15th - Aug 30th) utilizing the following parameters: Chlorophyl A, Suspended Solids, BOD-Total, Chloride, (Alk, pH, Cond), Total P, Total Kjeldahl-N, Nitrate&Nitrite, Ammonia-N {Dependent upon Bloom severity}. During peak algae bloom and macrophyte senescence periods on the Chetek Chain of Lakes (July 15th-August 30th) collect weekly samples on both the Chetek Chain of Lakes and the Chetek River to assess their current ecological health and to determine what proportion of the total nutrient and sediment loadings to the Red Cedar River are coming from land uses in the upper Red Cedar River when compared to those nutrient and sediment loadings or additions coming from the Chetek River during August when peak Algae blooms and macrophyte senecence on the Chetek Chain of Lakes are believed to be a dominant source in the upper Red Cedar River Basin.
i) | Partner Contributions - will others (outside DNR) contribute time and/or money to the project? If yes, describe briefly. | Barron County - will be working with us to control problem sources around the Chetek Chain of Lakes

## Project Budget
PLEASE FILL IN THE YELLOW HIGHLIGHTED CELLS Grey Cells Populate Automatically USE TABS BELOW TO SWITCH BETWEEN WORKSHEETS
Project Budget - State FY 2008
July 1, 2007 - June 30, 2008
1 | FTE Hours | 260
2 | LTE Information |  | Computed LTE Salary
| 2a - Hours Needed | 380 | 6481.0808
| 2b - Hourly Wage | 12
| 2c - Fringe @24.58% of Salary | 3.306
| 2d - Indirect @11.43% of (Salary + Fringe) | 1.7495
3 | Supplies |  | 100
4 | Travel |  | 700
5 | Contractual |  | 0
6 | Equipment <$5,000 |  | 4000
7 | Capital Equipment >$5,000 |  | 15000
8 | DNR Contributions: Sub-total: |  | 26281.0808
9 | Partner Contributions |  | 0
10 | SLOH Lab Services* |  | 5397.84
11 | Total Cost of Project |  | 31678.9208
* If requesting SLH support, the attached worksheet must be completed.

## SLOH Worksheet
PLEASE FILL IN THE YELLOW HIGHLIGHTED CELLS Grey Cells Populate Automatically USE TABS BELOW TO SWITCH BETWEEN WORKSHEETS
Basic Agreement Water Quality Monitoring
Collector/Submitter Name: | Jim Cahow
Project Name: | Chetek River - Algae Bloom & Peak Macrophyte senecence event sampling & Diurnal D.O. studies
Activity Category Name/Code: | Project Category 2c - a Continuation of previously approved special studies
Activity Name/Code: | Surface Water Quality Monitoring - 303d list activities
Project Number*:
Mon. Activity Code: | WTSK
SLOH Acct. Code*: | WT082
FY of Analysis: | FY 2008
* For requests to use the SLOH Basic Aggreement Resources, this form must be completed and submitted for review and approval by______ before samples may be submitted. The Test Request forms must be completed using the appropriate codes or the sample may
Test ID | Test Description | RVU/Test | # of | Total for
|  |  | Samples | Test
Bacti | Price per RVU = | 15.75
B200ALT | MFFCC | 0.8 |  | 0
B152ALT | E COLI ENZYMATIC SUBTRATE QUANTITRAY MPN | 1.5 |  | 0
B210ALT | FECAL STREPTOCOCCI | 0.9 |  | 0
Inorganics | Price per RVU = | 11.9
Nutrients
I440NLD | AMMONIA-N (SM 4500-NH3H) | 2 | 24 | 571.2
I460MLD | NITRATE PLUS NITRITE-N | 2 | 24 | 571.2
I470BLT | TOTAL KJELDAHL NITROGEN | 2.1 | 24 | 599.76
I520PLT | TOTAL PHOSPHORUS | 1.5 | 24 | 428.4
I530ALD | ORTHOPHOSPHATE AS P, LOW RANGE | 2.5 |  | 0
Solids
I640FLT | TOTAL SOLIDS | 1.5 |  | 0
I640GLT | TOTAL VOLATILE SOLIDS | 1 |  | 0
I650HLT | SUSPENDED SOLIDS | 1.9 | 24 | 542.64
I650HLT | VOLATILE SUSPENDED SOLIDS | 1 |  | 0
I640FLD + I640FLT | TOTAL DISSOLVED SOLIDS, 180 C, PLUS TOTAL SOLIDS | 3.4 |  | 0
I660ALT | TURBIDITY | 0.9 |  | 0
Misc.
I120ALT | ALKALINITY, GRAN TECHNIQUE | 3 |  | 0
I180ALT | BOD, 5 DAY | 3.7 | 24 | 1056.72
I240ELT | CHLORIDE | 1.5 | 24 | 428.4
I251UNF | CHLOROPHYLL A, FLUORESCENCE, FF (WELSCHMEYER 1994) | 2.3 |  | 0
I251UNL | CHLOROPHYLL A, FLUORESCENCE (WELSCHMEYER 1994) | 2.3 | 24 | 656.88
I280ALT | COD,LOW LEVEL | 2 |  | 0
I290ALT | COLOR, TRUE, PT-CO | 1.2 |  | 0
I305ALT | AUTOMATED CONDUCTIVITY, PH & ALKALINITY | 1.9 | 24 | 542.64
I320VUT | CYANIDE | 4 |  | 0
I500ALT | PH, LAB | 0.7 |  | 0
I410BLT | MBAS, COLORIMETRIC | 4.6 |  | 0
I560LLD | SILICA, DISSOLVED, LOW RANGE | 1.7 |  | 0
I600DLT | SULFATE, AUTOMATED | 1.9 |  | 0
I710ALT | FIELD TESTS (Required if field pH, DO, etc. on Lab Slip) | 0.4 |  | 0
Metals
| Hardness (Includes Ca, Mg, & Digestion) | 4 |  | 0
I370IDT | IRON, TOTAL , ICP | 1 |  | 0
I400IDT | MANGANESE, TOTAL , ICP | 1 |  | 0
I540IDT | POTASSIUM, TOTAL , ICP | 1 |  | 0
I580IDT | SODIUM, TOTAL , ICP | 1 |  | 0
I322IDT | DIGESTION, TOTAL , LIQUIDS, ICP + ICP SETUP | 2 | 0 | 0
ICP Panels
| Ca+Mg+Na+Hardness, Total | 3.3 | 0 | 0
| Ca+Mg+Na+Mn+Fe+K+Zn+Hardness, Total | 7.3 | 0 | 0
I322IDT | DIGESTION, TOTAL , LIQUIDS, ICP + ICP SETUP | 2 | 0 | 0
Trace Low Level Metals
I323ZDR | DIG, TOT REC, IN BOTTLE, ICPMS | 1 | 0 | 0
I495PBC | CLEAN BOTTLE PREP | 1.8 | 0 | 0
I860ZUT | ICP-MS 11 TOTAL RECOVERABLE (11.3RV + 0.7RV per element) | 13.7 |  | 0
I430ZDT | Mercury, Atomic Fluorescence, (low level) | 5.3 |  | 0
I495ZBC | Clean Bottle Prep, Hg (low level)(glass) | 1.4 | 0 | 0
Biomonitoring
CHRONIC TEST WITH FATHEAD MINNOW
CHRONIC TEST WITH CERIODAPHNIA d.
CHRONIC TEST WITH DAPHNIA m.
ACUTE TEST WITH FATHEAD MINNOW
ACUTE TEST WITH CERIODAPHNIA d.
ACUTE TEST WITH DAPHNIA m.
ACUTE LOW VOLUME SCREEN
MICROTOX TEST
(Note: Cost for biomonitoring samples funded differently)
|  | SLOH Total = |  | 5397.84