**Village of Somers Neumiller Woods Wetland Restoration Project**

**Quarterly Activity Reporting**

**Jerry Smith**

**Village of Somers**

**7511, 12th Street**

**Somers, WI 53171**

2/27/2019

Neumiller Woods site visit by Aaron Menke with Thompson and Associated to evaluate site conditions. Aaron evaluated that the site had 1-4 inches of ice covering the surface with 4-6 inches of water below the ice. Aaron evaluated that the site was not acceptable to allow the start of excavation.

3/27/2018

Neumiller Woods site visit by Jerry Smith of the Village of Somers. Site is under water to a depth of 6-8 inches and will require drying.

**QUARTERLY REPORT**

**JANUARY 1, 2019 - March 31, 2019**

**Expenditures**

No expenditures have occurred this period, pending invoicing from contracting organizations.

**Project Activities**

**Construction Schedule**

Due to standing water conditions throughout the quarterly period no construction activities were able to be performed. The Construction Schedule will be reviewed and amended with the intent of attempting construction at a later period.

**Environmental Services**

Site visits were performed by Thompson and Associates.

**Construction Activities**

No construction activities were able to be performed due to ice and standing water conditions.

**QAPP**

The QAPP is filed and approved, and will be evaluated periodically to the schedule pertaining to the availability to perform construction activities.

**Anticipated Next Quarter Activities**

The site will be evaluated on a regular basis to determine favorable conditions that will allowing construction activities. The stream flow and standing water will be evaluated and if the 2nd quarter has minimal precipitation that allows the site to dry the start of construction will be evaluated.