Lake Puckaway Biannual Grant Implementation Report

December 31, 2011

Project 20% complete

Weekly

- Blog updates and communication

Biweekly

- Water level monitoring at 3 stations

July through September

- Water quality monitoring at 8 stations

- Endangered bird surveys

August

- Aquatic vegetation survey

- Site exploration for emergent plant seedling establishment

September

- Finish trophic monitoring

October

- Plan shoreland restoration program, public notice accepting applications

November

- Shoreland restoration project applications reviewed and sites visited.

December

- Planning for sediment deposition and erosion control “crib” wall constructed of cedar posts and re-used Christmas trees.

- Writing 2011 trophic monitoring report