GRANT CLOSE-OUT CHECKLIST

BIG ROUND LAKE CBCW AIS EDUCATION AND PREVENTION

Big Round Lake

AEPP-322-12

Upon project completion, the sponsor will provide the state with a comprehensive report including:

 1)   Final Report summarizing accomplishments/progress of the grant.

Paper and electronic copy of report are to be submitted.

Watercraft inspection and lake monitoring (CBCW & ILIDS).

  Report on installation of ILIDS device

  Signage

NOTES:  12 Dec 2012 – Received Progress Report.

14 Jan 2013 – 85 hours CBCW hours in SWIMS. Contacted Sponsor to remind them of the 200 hour requirement.

9 Jan 2015 – Requested electronic copy of Final Report (Gordon  Kill).

12 Jan 2015 – Received electronic copy of Final Report.  CBCW activity is described in the SWIMS database along with

boater questionnaire results.  ILIDS activity is described in the Final Report.  Final Report describes ILIDS

installation and challenges (lighting, parts ordering, and trees obstructing solar panel). Problems with installation

resulted in interruption of video download for  two months in 2014.  Final Report includes picture of ILIDS camera

installation and signage.

 2)   Financial Payment Request with documentation of grant administration

time and services and proof of payments for reimbursement.

NOTES:   12 Dec 2012 - Received Partial Payment Request (includes ILIDS)  14 Jan 2013 – APPROVED

9 Jan 2015 – Received Final Payment Request

  3) Watercraft inspection report including time and number of people reached;

CB/CW survey results; daily results will be entered into the DNR CB/CW database.

NOTES: 14 Jan 2013 – 85 hours CBCW hours in SWIMS including number of people reached.  Participated in July 4 CB/CW Blitz.

9 Jan 2015 – 75 paid CBCW hours and 159.5 volunteer CBCW hours in SWIMS including number of people reached.

Met /exceeded 200 hour requirement for 2014.  Participated in July 4 CB/CW Blitz.

 4) ILIDS inspection report including time and number of launches and potential violations

NOTES:  12 Jan 2015 – Received Electronic copy of ILIDS Report detailing launch activity, times, number of launches,

and notable observations.  No AIS Violations observed.

 5)  Verification of workshops and/or inspector training such as agendas and attendance lists.

NOTES:  12 Jan 2015 – Final Report does not address training.  CBCW boat inspectors were trained at beginning of grant.

No charges to final grant payment.

 6)  Copies of press releases/newsletters/educational materials distributed to the public.

NOTES:  12 Dec 2012 – Copy of CB/CW brochure attached to Progress Report.

 7)  AIS related materials generated or paid for by this grant.

NOTES:  12 Jan 2015 – No additional charges incurred through this grant.

APPROVED FOR PAYMENT

___________________________________  Date _________