## UNRANKED
Potato Lake Comprehensive Management Plan - Implementation and Funding Matrix
Plan Element |  | Priority Level | Responsible Parties | Estimated Cost | Sources of Funding | Year 1 2014 | Year 2 2015 | Year 3 2016 | Year 4 2017 | Year 5 2018
Goal 1 - Reduce sediment and phosphorus entering the lake
Up-to-date septic tank inspection and repair
| Remind property owners via newsletter or other media |  | PLA | minimal | PLA, LP | x | x | x | x | x
Encourage greater use of Agricultural Best Management Practices (BMPs) in the watershed
| Provide educational and information materials to local farmers on BMP |  | LWCD, PLA, Local Ag, UWEX | minimal | County, NRCS, PLA, LP | x | x | x | x | x
| Facilitate communication and cooperation between lake residents and local farmers |  | PLA, Ag, LWCD | minimal | PLA, County, LP | x | x | x | x | x
| Evaluate and consider a BMP incentives program for local farmers |  | LWCD, PLA, Ag | minimal | PLA, County, LP | x
| Implement BMP incentives program for local farmers |  | LWCD, Ag, NRCS, PLA | Varies with programs | PLA, County, LP |  | ? | ? | ? | ?
Encourage implementation of shoreland and in-lake best management practices
| Identify property owners willing to implement runoff reduction practices; seek grant funding to aid in design and implementation |  | PLA, Riparians | minimal | PLA, LP | x | x | x | x | x
| Sponsor and promote a shoreland restoration and rain garden workshop |  | PLA, LWCD, RP | 2000 | PLA, County, LP | x |  | x |  | x
| Provide education and informational materials for ecologically friendly shoreland protection and uses |  | PLA, UWEX, LWCD | minimal | PLA, LP | x | x | x | x | x
| Evaluate the need for and design and installation of a detention basin to contain runoff from the public boat landing |  | PLA, Township, County, WDNR | minimal | SLP | ? | ?
| Recognize property owners who install best management practices |  | PLA, UWEX, LWCD | minimal | PLA, LP | x | x | x | x | x
Monitor water quality through the Citizen Lake Monitoring Network
| Recruit and support volunteer monitors |  | PLA, WDNR | minimal | PLA, LP, CLMN | x | x | x | x | x
| Evaluate sampling efforts annually based on data needs and changes to lake |  | PLA, RP, WDNR | (RP: ~$500/year) | PLA, LP | x | x | x | x | x
| Install and maintain a permanent bench mark and staff gauge to monitor water levels |  | PLA, County, Township, RP | Installation and survey: $500 Annual survey: $150 | PLA, LP | x | x | x | x | x
Goal 2 - Promote sustainable and multi-use recreational opportunities
Evaluate need for a lake-use plan
| Monitor recreational use patterns to guide outreach efforts |  | PLA | minimal | PLA | x | x
| Hold open forums to discuss lake use issues with interested parties |  | PLA, Riparians | 200 | PLA | x | x | x | x | x
| Develop, implement, and evaluate a Lake-Use Plan that may include new lake use ordinances |  | PLA, RP, Town, County | 6000 | SPL Grant |  |  | x | x | x
Actively engage the public in lake management efforts
| Encourage involvement and participation in lake association functions |  | PLA | minimal | PLA, LP | x | x | x | x | x
| Hold an annual lake fair, picnic, or other special event |  | PLA | 300 | PLA, LP | x | x | x | x | x
| Sponsor special projects and public forums related to lake management |  | PLA |  | PLA, LP | x | x | x | x | x
| Publish a newsletter (annual basis at the minimum) |  | PLA | 250 | PLA, LP | x | x | x | x | x
| Involve volunteers in lake monitoring programs (CLMN, CBCW, wildlife, AIS monitoring) |  | PLA, WDNR, UWEX | minimal | PLA, LP | x | x | x | x | x
Goal 3 - Maintain and improve current fishery and wildlife habitat
Improve riparian and littoral zone habitat
| Develop coarse woody structure management goals |  | PLA, WDNR | minimal | WDNR | x | x | x | x | x
| Install and maintain riparian buffer strips that include herbaceous cover, shrubs and young trees, and mature trees |  | PLA, WDNR | ~$2 per linear foot | PLA, WDNR, LWCD | x
Minimize potential impacts to fishery that may be caused by lake management activities
| Meet annually with WDNR to discuss current fishery management activities and to identify lake management activities that may be in conflict |  | PLA, WDNR | minimal | WDNR | x | x | x | x | x
Develop a critical habitat protection plan for the lake
| Communicate desire for a critical habitat area study and report to WDNR |  | PLA | minimal | WDNR | x | x | x | x | x
Goal 4 - Implement Aquatic Plant Management Plan
Follow goals, objectives and actions in the 2010 APM Plan
| Update 2010 APM Plan |  | PLA, RP | 10000 | PLA, AIS Grant |  | x
| Implement aquatic plant management actions in the new APM Plan |  | PLA, RP |  | PLA, AIS Grant |  |  | x | x | x
Goal 5 - Implement CLM Plan activities and maintain plan
Use an adaptive management approach when implementing this plan
| Complete annual reports (summary of events/activities, suggested strategy revisions, future management plans) |  | PLA, RP |  | PLA, LP | x | x | x | x | x
| Integrate new information and planning elements as they become available |  | PLA, RP |  | PLA, LP | x | x | x | x | x
Secure funding to implementation of this Comprehensive Lake Management Plan
| Utilize WDNR Lake Protection grants for implementation of management activities |  | PLA |  | LP | x | x | x | x | x
| Identify other funding sources for implementation of management activities |  | PLA |  | Partners, fund raising | x | x | x | x | x
Abbreviations: PLA, Potato Lake Association; LWCD, Washburn County Land & Water Conservation Dept.; NRCS, U.S. Department of Agriculture-Natural Resources Conservation Service; WDNR, Wisconsin Department of Natural Resources; County, Washburn County; Township, Townships of Crystal and Madge; RP, resource professionals/consultant; UWEX, University of Wisconsin Extension; Riparians, lake property owners; Ag, local farmers and ranchers; LP, WDNR lake protection grant; SLP, small-scale lake planning grant; CBMN, Citizen Based Monitoring Network; CLMN, Citizen Lake Monitoring Network; CBCW, Clean Boats Clean Waters; NA, not applicable.
Note: Responsible parties and sources of funding are not exhaustive and could change; Grant eligibility is subject to WDNR approval. It is always the repsonsibility of the Potato Lake Association to intiate these activities by contacting potential partners (Responsible Parties) and Funding Sources.

## Rankings
Potato Lake Comprehensive Management Plan - Implementation and Funding Matrix
Plan Element |  | Priority Level | [5 empty] | Responsible Parties | Estimated Cost | Sources of Funding | Year 1 2014 | Year 2 2015 | Year 3 2016 | Year 4 2017 | Year 5 2018
Goal 1 - Reduce sediment and phosphorus entering the lake |  |  | JA | HW | JW | KC | average
Up-to-date septic tank inspection and repair
| Remind property owners via newsletter or other media | 2.5 | 5 | 1 | 1 | 3 | 2.5 | PLA | minimal | PLA, LP | x | x | x | x | x
Encourage greater use of Agricultural Best Management Practices (BMPs) in the watershed
| Provide educational and information materials to local farmers on BMP | 4 | 5 | 4 | 3 | 4 | 4 | LWCD, PLA, Local Ag, UWEX | minimal | County, NRCS, PLA, LP | x | x | x | x | x
| Facilitate communication and cooperation between lake residents and local farmers | 4.25 | 5 | 4 | 4 | 4 | 4.25 | PLA, Ag, LWCD | minimal | PLA, County, LP | x | x | x | x | x
| Evaluate and consider a BMP incentives program for local farmers | 4.5 | 5 | 4 | 5 | 4 | 4.5 | LWCD, PLA, Ag | minimal | PLA, County, LP | x
| Implement BMP incentives program for local farmers | 4.5 | 5 | 4 | 5 | 4 | 4.5 | LWCD, Ag, NRCS, PLA | Varies with programs | PLA, County, LP |  | ? | ? | ? | ?
Encourage implementation of shoreland and in-lake best management practices
| Identify property owners willing to implement runoff reduction practices; seek grant funding to aid in design and implementation | 2.25 | 3 | 3 | 2 | 1 | 2.25 | PLA, Riparians | minimal | PLA, LP | x | x | x | x | x
| Sponsor and promote a shoreland restoration and rain garden workshop | 3 | 3 | 3 | 4 | 2 | 3 | PLA, LWCD, RP | 2000 | PLA, County, LP | x |  | x |  | x
| Provide education and informational materials for ecologically friendly shoreland protection and uses | 2 | 2 | 2 | 2 | 2 | 2 | PLA, UWEX, LWCD | minimal | PLA, LP | x | x | x | x | x
| Evaluate the need for and design and installation of a detention basin to contain runoff from the public boat landing | 2 | 4 | 2 | 1 | 1 | 2 | PLA, Township, County, WDNR | minimal | SLP | ? | ?
| Recognize property owners who install best management practices | 2.5 | 3 | 2 | 4 | 1 | 2.5 | PLA, UWEX, LWCD | minimal | PLA, LP | x | x | x | x | x
Monitor water quality through the Citizen Lake Monitoring Network
| Recruit and support volunteer monitors | 1.25 | 1 | 2 | 1 | 1 | 1.25 | PLA, WDNR | minimal | PLA, LP, CLMN | x | x | x | x | x
| Evaluate sampling efforts annually based on data needs and changes to lake | 1 | 1 | 1 | 1 | 1 | 1 | PLA, RP, WDNR | (RP: ~$500/year) | PLA, LP | x | x | x | x | x
| Install and maintain a permanent bench mark and staff gauge to monitor water levels | 1.25 | 1 | 1 | 1 | 2 | 1.25 | PLA, County, Township, RP | Installation and survey: $500 Annual survey: $150 | PLA, LP | x | x | x | x | x
Goal 2 - Promote sustainable and multi-use recreational opportunities
Evaluate need for a lake-use plan
| Monitor recreational use patterns to guide outreach efforts | 2.5 | 2 | 2 | 5 | 1 | 2.5 | PLA | minimal | PLA | x | x
| Hold open forums to discuss lake use issues with interested parties | 2.25 | 2 | 2 | 4 | 1 | 2.25 | PLA, Riparians | 200 | PLA | x | x | x | x | x
| Develop, implement, and evaluate a Lake-Use Plan that may include new lake use ordinances | 2.75 | 4 | 2 | 3 | 2 | 2.75 | PLA, RP, Town, County | 6000 | SPL Grant |  |  | x | x | x
Actively engage the public in lake management efforts
| Encourage involvement and participation in lake association functions | 1.25 | 1 | 1 | 1 | 2 | 1.25 | PLA | minimal | PLA, LP | x | x | x | x | x
| Hold an annual lake fair, picnic, or other special event | 1.25 | 1 | 1 | 1 | 2 | 1.25 | PLA | 300 | PLA, LP | x | x | x | x | x
| Sponsor special projects and public forums related to lake management | 2.75 | 2 | 2 | 5 | 2 | 2.75 | PLA |  | PLA, LP | x | x | x | x | x
| Publish a newsletter (annual basis at the minimum) | 1 | 1 | 1 | 1 | 1 | 1 | PLA | 250 | PLA, LP | x | x | x | x | x
| Involve volunteers in lake monitoring programs (CLMN, CBCW, wildlife, AIS monitoring) | 1.75 | 2 | 2 | 2 | 1 | 1.75 | PLA, WDNR, UWEX | minimal | PLA, LP | x | x | x | x | x
Goal 3 - Maintain and improve current fishery and wildlife habitat
Improve riparian and littoral zone habitat
| Develop coarse woody structure management goals | 2.75 | 2 | 1 | 5 | 3 | 2.75 | PLA, WDNR | minimal | WDNR | x | x | x | x | x
| Install and maintain riparian buffer strips that include herbaceous cover, shrubs and young trees, and mature trees | 2 | 3 | 2 | 2 | 1 | 2 | PLA, WDNR | ~$2 per linear foot | PLA, WDNR, LWCD | x
Minimize potential impacts to fishery that may be caused by lake management activities |  | 3 |  |  | 3 |  | 3
| Meet annually with WDNR to discuss current fishery management activities and to identify lake management activities that may be in conflict | 1.5 | 2 | 1 | 2 | 1 | 1.5 | PLA, WDNR | minimal | WDNR | x | x | x | x | x
Develop a critical habitat protection plan for the lake |  | 0
| Communicate desire for a critical habitat area study and report to WDNR | 3.25 | 3 | 3 | 5 | 2 | 3.25 | PLA | minimal | WDNR | x | x | x | x | x
Goal 4 - Implement Aquatic Plant Management Plan
Follow goals, objectives and actions in the 2010 APM Plan
| Update 2010 APM Plan | 3.25 | 2 | 3 | 5 | 3 | 3.25 | PLA, RP | 10000 | PLA, AIS Grant |  | x
| Implement aquatic plant management actions in the new APM Plan | 2.75 | 2 | 3 | 3 | 3 | 2.75 | PLA, RP |  | PLA, AIS Grant |  |  | x | x | x
Goal 5 - Implement CLM Plan activities and maintain plan
Use an adaptive management approach when implementing this plan
| Complete annual reports (summary of events/activities, suggested strategy revisions, future management plans) | 2.5 | 2 | 3 | 3 | 2 | 2.5 | PLA, RP |  | PLA, LP | x | x | x | x | x
| Integrate new information and planning elements as they become available | 3 | 2 | 3 | 5 | 2 | 3 | PLA, RP |  | PLA, LP | x | x | x | x | x
Secure funding to implementation of this Comprehensive Lake Management Plan
| Utilize WDNR Lake Protection grants for implementation of management activities | 2 | 2 | 1 | 3 | 2 | 2 | PLA |  | LP | x | x | x | x | x
| Identify other funding sources for implementation of management activities | 3 | 3 | 1 | 5 | 3 | 3 | PLA |  | Partners, fund raising | x | x | x | x | x
Abbreviations: PLA, Potato Lake Association; LWCD, Washburn County Land & Water Conservation Dept.; NRCS, U.S. Department of Agriculture-Natural Resources Conservation Service; WDNR, Wisconsin Department of Natural Resources; County, Washburn County; Township, Townships of Crystal and Madge; RP, resource professionals/consultant; UWEX, University of Wisconsin Extension; Riparians, lake property owners; Ag, local farmers and ranchers; LP, WDNR lake protection grant; SLP, small-scale lake planning grant; CBMN, Citizen Based Monitoring Network; CLMN, Citizen Lake Monitoring Network; CBCW, Clean Boats Clean Waters; NA, not applicable.
Note: Responsible parties and sources of funding are not exhaustive and could change; Grant eligibility is subject to WDNR approval. It is always the repsonsibility of the Potato Lake Association to intiate these activities by contacting potential partners (Responsible Parties) and Funding Sources.

## FINAL
Potato Lake Comprehensive Management Plan - Implementation and Funding Matrix
Plan Element |  | Priority Level | Responsible Parties | Estimated Cost | Sources of Funding | Year 1 2014 | Year 2 2015 | Year 3 2016 | Year 4 2017 | Year 5 2018
Goal 1 - Reduce sediment and phosphorus entering the lake
Up-to-date septic tank inspection and repair
| Remind property owners via newsletter or other media | 2.5 | PLA | minimal | PLA, LP | x | x | x | x | x
Encourage greater use of Agricultural Best Management Practices (BMPs) in the watershed
| Provide educational and information materials to local farmers on BMP | 4 | LWCD, PLA, Local Ag, UWEX | minimal | County, NRCS, PLA, LP | x | x | x | x | x
| Facilitate communication and cooperation between lake residents and local farmers | 4.25 | PLA, Ag, LWCD | minimal | PLA, County, LP | x | x | x | x | x
| Evaluate and consider a BMP incentives program for local farmers | 4.5 | LWCD, PLA, Ag | minimal | PLA, County, LP | x
| Implement BMP incentives program for local farmers | 4.5 | LWCD, Ag, NRCS, PLA | Varies with programs | PLA, County, LP |  | ? | ? | ? | ?
Encourage implementation of shoreland and in-lake best management practices
| Identify property owners willing to implement runoff reduction practices; seek grant funding to aid in design and implementation | 2.25 | PLA, Riparians | minimal | PLA, LP | x | x | x | x | x
| Sponsor and promote a shoreland restoration and rain garden workshop | 3 | PLA, LWCD, RP | 2000 | PLA, County, LP | x |  | x |  | x
| Provide education and informational materials for ecologically friendly shoreland protection and uses | 2 | PLA, UWEX, LWCD | minimal | PLA, LP | x | x | x | x | x
| Evaluate the need for and design and installation of a detention basin to contain runoff from the public boat landing | 2 | PLA, Township, County, WDNR | minimal | SLP | ? | ?
| Recognize property owners who install best management practices | 2.5 | PLA, UWEX, LWCD | minimal | PLA, LP | x | x | x | x | x
Monitor water quality through the Citizen Lake Monitoring Network
| Recruit and support volunteer monitors | 1.25 | PLA, WDNR | minimal | PLA, LP, CLMN | x | x | x | x | x
| Evaluate sampling efforts annually based on data needs and changes to lake | 1 | PLA, RP, WDNR | (RP: ~$500/year) | PLA, LP | x | x | x | x | x
| Install and maintain a permanent bench mark and staff gauge to monitor water levels | 1.25 | PLA, County, Township, RP | Installation and survey: $500 Annual survey: $150 | PLA, LP | x | x | x | x | x
Goal 2 - Promote sustainable and multi-use recreational opportunities
Evaluate need for a lake-use plan
| Monitor recreational use patterns to guide outreach efforts | 2.5 | PLA | minimal | PLA | x | x
| Hold open forums to discuss lake use issues with interested parties | 2.25 | PLA, Riparians | 200 | PLA | x | x | x | x | x
| Develop, implement, and evaluate a Lake-Use Plan that may include new lake use ordinances | 2.75 | PLA, RP, Town, County | 6000 | SPL Grant |  |  | x | x | x
Actively engage the public in lake management efforts
| Encourage involvement and participation in lake association functions | 1.25 | PLA | minimal | PLA, LP | x | x | x | x | x
| Hold an annual lake fair, picnic, or other special event | 1.25 | PLA | 300 | PLA, LP | x | x | x | x | x
| Sponsor special projects and public forums related to lake management | 2.75 | PLA |  | PLA, LP | x | x | x | x | x
| Publish a newsletter (annual basis at the minimum) | 1 | PLA | 250 | PLA, LP | x | x | x | x | x
| Involve volunteers in lake monitoring programs (CLMN, CBCW, wildlife, AIS monitoring) | 1.75 | PLA, WDNR, UWEX | minimal | PLA, LP | x | x | x | x | x
Goal 3 - Maintain and improve current fishery and wildlife habitat
Improve riparian and littoral zone habitat
| Develop coarse woody structure management goals | 2.75 | PLA, WDNR | minimal | WDNR | x | x | x | x | x
| Install and maintain riparian buffer strips that include herbaceous cover, shrubs and young trees, and mature trees | 2 | PLA, WDNR | ~$2 per linear foot | PLA, WDNR, LWCD | x
Minimize potential impacts to fishery that may be caused by lake management activities |  | 3
| Meet annually with WDNR to discuss current fishery management activities and to identify lake management activities that may be in conflict | 1.5 | PLA, WDNR | minimal | WDNR | x | x | x | x | x
Develop a critical habitat protection plan for the lake |  | 0
| Communicate desire for a critical habitat area study and report to WDNR | 3.25 | PLA | minimal | WDNR | x | x | x | x | x
Goal 4 - Implement Aquatic Plant Management Plan
Follow goals, objectives and actions in the 2010 APM Plan
| Update 2010 APM Plan | 3.25 | PLA, RP | 10000 | PLA, AIS Grant |  | x
| Implement aquatic plant management actions in the new APM Plan | 2.75 | PLA, RP |  | PLA, AIS Grant |  |  | x | x | x
Goal 5 - Implement CLM Plan activities and maintain plan
Use an adaptive management approach when implementing this plan
| Complete annual reports (summary of events/activities, suggested strategy revisions, future management plans) | 2.5 | PLA, RP |  | PLA, LP | x | x | x | x | x
| Integrate new information and planning elements as they become available | 3 | PLA, RP |  | PLA, LP | x | x | x | x | x
Secure funding to implementation of this Comprehensive Lake Management Plan
| Utilize WDNR Lake Protection grants for implementation of management activities | 2 | PLA |  | LP | x | x | x | x | x
| Identify other funding sources for implementation of management activities | 3 | PLA |  | Partners, fund raising | x | x | x | x | x
Abbreviations: PLA, Potato Lake Association; LWCD, Washburn County Land & Water Conservation Dept.; NRCS, U.S. Department of Agriculture-Natural Resources Conservation Service; WDNR, Wisconsin Department of Natural Resources; County, Washburn County; Township, Townships of Crystal and Madge; RP, resource professionals/consultant; UWEX, University of Wisconsin Extension; Riparians, lake property owners; Ag, local farmers and ranchers; LP, WDNR lake protection grant; SLP, small-scale lake planning grant; CBMN, Citizen Based Monitoring Network; CLMN, Citizen Lake Monitoring Network; CBCW, Clean Boats Clean Waters; NA, not applicable.
Note: Responsible parties and sources of funding are not exhaustive and could change; Grant eligibility is subject to WDNR approval. It is always the repsonsibility of the Potato Lake Association to intiate these activities by contacting potential partners (Responsible Parties) and Funding Sources.