## Jar Test Log
Jar Test Log for Long Lake, WI Alum Application - 2020
Post-dose pH measured in jar 15 minutes after adding the alum dose
Date | Lake | Time | Percent of Total Dose | Pre-dose pH | Post-dose pH | Notes
2020-06-22 | Long | 5:35 | 100 | 8.56 | 6.71
2020-06-22 | Long | 5:35 | 70* | 8.56 | 6.94 | *assumes 70% of total dose will be applied in day 1
2020-06-23 | Long | 6:00 | 30* | 7.34 | 6.8 | *assumes 30% of total dose will be applied in day 2

## Daily Application Log
Daily Application Log for Long Lake, WI Alum Application - 2020
Date | Lake | Hours of Application | Approx. Alum Applied (gal) | Approx. Acres Covered* | Alum Truck Deliveries | Notes
2020-06-22 | Long | 6:05 - 16:35 | 30133 | 64.8 | 7 | First day of application
2020-06-23 | Long | 6:35 - 9:35 | 10474 | 22.4 | 3 | Application completed
Total |  |  | 40607 | 87.2 | 10 |  | Alum Target Dose (gal) | Gallons Remaining | % Complete
[7 empty] | 40496 | -111 | 100.2741

## BOL Worksheet
Long Lake, WI - 2020
Alum | Date | Product | BOL # | lbs | gallons
1 | 2020-06-22 | ALUM | 1001 | 48140 | 4336.9369
2 | 2020-06-22 | ALUM | 1002 | 49240 | 4436.036
3 | 2020-06-22 | ALUM | 1003 | 48920 | 4407.2072
4 | 2020-06-22 | ALUM | 1004 | 46980 | 4232.4324
5 | 2020-06-22 | ALUM | 1005 | 49580 | 4466.6667
6 | 2020-06-22 | ALUM | 1006 | 47320 | 4263.0631
7 | 2020-06-22 | ALUM | 1007 | 48280 | 4349.5495
8 | 2020-06-23 | ALUM | 1008 | 48940 | 4409.009
9 | 2020-06-23 | ALUM | 1009 | 46600 | 4198.1982
10 | 2020-06-23 | ALUM | 1010 | 16740 | 1508.1081
Total |  |  |  | 450740 | 40607.2072
Target Dose (gal) | Gallons Remaining | % Complete
40496 | -111.2072 | 100.2746

## Lake pH Log
Lake pH Log for Long Lake, WI Alum Application - 2020
All readings taken 0.25 m below surface
Date | Lake | Time | pH outside of floc zone | pH inside of floc zone | Notes
2020-06-22 | Long | 6:25 | 8.12 | 7.26
2020-06-22 | Long | 8:30 | 8.24 | 7.33
2020-06-22 | Long | 9:35 | 8.36 | 7.3
2020-06-22 | Long | 10:25 | 8.41 | 7.45
2020-06-22 | Long | 11:30 | 8.1 | 7.08
2020-06-22 | Long | 12:40 | 7.86 | 7.11
2020-06-22 | Long | 13:25 | 7.8 | 7.14
2020-06-22 | Long | 14:35 | 7.61 | 6.96
2020-06-22 | Long | 15:20 | 7.54 | 6.91
2020-06-22 | Long | 16:20 | 7.4 | 6.88
2020-06-23 | Long | 6:50 | 7.73 | 6.81
2020-06-23 | Long | 7:45 | 7.69 | 6.91
2020-06-23 | Long | 8:40 | 7.52 | 6.84
2020-06-23 | Long | 9:50 | 7.5 | 7.05