Upper Sugar River Watershed Association
Conservation Field Assistant reporting document
North: Crawford, Richland, Sauk, Vernon
South: Dane, Grant, Green, Iowa, Lafayette
(North and South)
5/27/2020 to 10/23/2020

Goal 1: Education

Activity 1A: EDUCATE OUTDOOR RECREATIONISTS, SPORTSPEOPLE, WATER GARDENERS, AND AQUARISTS

Aquatic Invasive Species (AIS) Paddles

Method: Attend paddle with supervisors to scout for AIS.
Deliverable: Paddled on Sugar River – no AIS identified.
Timeline: Fieldwork Season (June-Oct 2020)
County: Dane

Paddle Sugar river with Wade Moder and volunteers Bill and Lisa Keen from Valley Road to Paoli – no AIS identified (7/16/2020).

Bait Campaign

Method: Expand Bait dealer campaign in all counties within grants.
Deliverable: Visited 36 bait shops to participate in Bait Campaign.
Timeline: Fieldwork Season (June-Oct 2020)
Counties: Sauk, Vernon, Crawford, Iowa, Grant, Lafayette, Green, Dane

Plan and map out shops to visit along Mississippi (6/24,26/2020).
36 shop visits: 11 in North (4 new) & 25 in South (18 new)
Link with list of visits (new visits in bold):
https://docs.google.com/spreadsheets/d/1VHCTpF_3PKeXjKdcRpL3xkF0-u3XbvfzEr_cCB5CVGs/edit#gid=1753095799

Organisms in Trade (OIT)

Method: OIT Habitattitude campaign.
Deliverable: 10 OIT contacts and Pet Surrender event.
Timeline: Fieldwork Season (June-Oct 2020)
Counties: Crawford, Vernon, Sauk, Dane, Grant

OIT inspection training @ Lakeside General Store 12965 WI-78 Trunk, Merrimac, WI 53561 (6/10/2020)
OIT inspection @ Nelson Agri-Center True Value 217 N Center Ave, Viroqua, WI 54665 (6/27/20)
OIT Habitatitude Campaign visits with Matt (10 total) (8/26/2020); link to list of visits:
https://docs.google.com/spreadsheets/d/1izN6h9FYVako4jfc2J01mxMw_TlZriu4wPme--3hp3c/edit#gid=0
Put up fliers around West Madison to advertise Pet Surrender event (10/5/2020).
Pet Surrender event Radisson Hotel Madison (10/16/2020).

AIS Signs

Method: Report presence/absence of AIS signs at landings.
Deliverable: Report presence/absence in SWIMS. Identify contacts to get permission to put up signs.
Timeline: Fieldwork Season (June-Oct 2020)
Counties: Crawford, Vernon, Sauk, Grant, Lafayette, Iowa, Dane

Report in SWIMS presence of AIS signs (including boots and brushes) at landings and water entry points that I drove by and/or visited for field work (28 present): Access points with signs (sheet 1).
Report in SWIMS absence of AIS signs at landings that I drove by and/or visited for field work
Landings needing AIS signs (9 absent): Landings needing AIS signs (sheet 2).
Research who is in charge of landings absent of signs and find their contact info so that Matt can send out comms to get signs up. Draft communication to asking permission to post signs using the DNR’s permission form and Sign Posting Instructions (found for 9 landings): Contacts for Landings Needing Signs (sheet 3).
https://docs.google.com/spreadsheets/d/1i83Jgo3eF7Dft0ZhguMOJIteyfNM3RR-7UD3EW_5nWQ/edit#gid=1769867417

Activity 1B: TRAIN GOVERNMENT PROFESSIONALS

Research AIS control successes, and Present to Gov. Units, Report Changes

N/A

Smart Mowing best management practices (BMP) to Gov units

N/A

Activity 1C: EDUCATE LANDOWNERS AND COMMUNITY MEMBERS

AIS ID class

N/A

AIS presentations to communities

N/A

Mechanical Removal techniques:

N/A

Goal 2: Prevention

Activity 2A: PARTICIPATE IN STATEWIDE BOAT LAUNCH PREVENTION CAMPAIGNS

June Drain Campaign

Method: Participate in the statewide Drain Campaign via CBCW.
Deliverable: 90 boaters reached through 5.75 hours of Drain Campaign.
Timeline: 6/28/2020-7/5/2020
Counties: Vernon, Crawford, Grant

In combination with Landing Blitz
Purpose: remind anglers not to transport live fish away from waterbodies and drain all water from boats, livewells, and other equipment. Emphasize icing catch as alternative.
CBCW along Mississippi River: Bad Axe Landing (2.25 hours, 6 contacts), Blackhawk Upper Access (1.5 hours, 34 people contacted), Ferryville Landing (0.75 hours, 2 contacts), St. Feriole Slough (0.75 hours, 29 people contacted), Cassville Public Access (0.5 hours, 19 contacts) (6/28/2020)
Total: 5.75 hours, 90 contacts

July Landing Blitz

Method: Participate in the statewide July 4th Landing Blitz via CBCW.
Deliverable: 172 boaters reached through 7 hours of July 4th Landing Blitz.
Timeline: 6/28/2020-7/5/2020
Counties: Sauk, Crawford, Grant

In combination with Drain Campaign.
Purpose: statewide effort to educate as many boaters as possible in one weekend.
CBCW at Moon Valley Landing, Lake Wisconsin: 3 hours, 70 contacts (7/3/2020).
CBCW at Cassville Public Landing (2 hours, 25 contacts) and St. Feriole Slough, Prairie du Chien (2 hours, 77 contacts) (7/5/2020).
Total: 7 hours, 172 contacts

WaterFowl Hunter (WFH)

Method: Recruit and train volunteers and self to participate in the statewide September Waterfowl Hunter Campaign, focusing on Mississippi River.
Deliverable: 24 hunters reached through 18.75 hours of outreach.
Timeline: September-October
Counties: Vernon, Crawford, Grant, Iowa

Research sites and landings along Mississippi and Wisconsin River in which we should focus outreach efforts (9/3,14/2020): https://docs.google.com/spreadsheets/d/10FB413riVjZ8EP0zq64NJarx7nGZGm_KfWE0GwTUvuY/edit?usp=sharing
Drafted phone call and email blurb for volunteer outreach (9/3,28-29/2020); link to phone call blurb: https://docs.google.com/document/d/1xSbUfwhH_h8mzfX-pjCklQoQ7-kRg5vDTO9KXIrBvPI/edit?usp=sharing and link to outreach email:
https://docs.google.com/document/d/1HYBxOLldKbsgHOy6PoSmZEzo3HVkiIuZpEUGpELQhjo/edit?usp=sharing
Outreach to community organizations to join WFH outreach: contacted 13 organizations (sheet 2) (9/15,17,28-29/2020); link to organizations that I contacted:
https://docs.google.com/spreadsheets/d/10FB413riVjZ8EP0zq64NJarx7nGZGm_KfWE0GwTUvuY/edit?usp=sharing
Planned (9/17,22/2020) and gave virtual volunteer training (9/23/2020); link to training video: https://www.youtube.com/watch?v=IsNATrFMoLQ
Scheduled two in-person volunteer trainings for WFH outreach: 10/3/2020 @ St. Feriole Slough Landing (0 attendees) and 10/9/2020 @ Cassville Public Landing (canceled due to change of locations).
Writing outreach blurb for social media push for volunteers to help with WFH outreach.
Waterfowl Hunter AIS Outreach:
- 10/3/2020 St. Feriole Slough Landing (5.5 hours, 2 contacts)
- 10/3/2020 Miss. River Ambro Access (0.5 hours, 0 contacts)
- 10/3/2020 Miss. River Ambro Slough Landing (0.5 hours, 0 contacts)
- 10/3/2020 Campion Landing (1.5 hours, 5 contacts)
- 10/4/2020 Kickapoo River Station 1 -1962 Boat Landing in Wauzeka (0.25 hours, 0 contacts)
- 10/4/2020 Winneshiek Slough Landing (2.5 hours, 6 contacts)
- 10/4/2020 WI River Boscobel (West) Von Haden (0.5 hours, 0 contacts)
- 10/4/2020 Avoca Lake Landing (0.5 hours, 0 contacts)
- 10/9/2020 Hunter’s Point Landing (South Goose Island) (4 hours, 11 contacts)
- 10/21/2020 Mazo Town Boat Landing (2 hours, 0 contacts)
- 10/22/2020 (1 hour, 0 contacts)
Total: 18.75 hours (14.75 North, 4 South), 24 contacts (all North)
Report on WFH Outreach (10/7/2020): https://docs.google.com/document/d/1sld_lgVqVCB8nvFKSTsjRW0CUyOeV7z1A4Rzj9SFqqE/edit?usp=sharing

Clean Boats Clean Waters (CBCW)

Method: Coordinate watercraft inspections through the CBCW program.
Deliverable: 637 boaters educated through 90.5 hours of CBCW program.
Timeline: Growing season (March-Sept)
Counties: Crawford, Sauk, Vernon, Grant, Iowa, Lafayette

CBCW training w/ DNR via Zoom, 2 hours (5/29/2020).
CBCW Training with Matt at Yellowstone Lake (6/4/2020).
Write CBCW article for tristate(?) newspaper (6/11,17/2020); link to article: https://docs.google.com/document/d/1oIfKWGRlJ4Kl4qsA0BnFJceKwyTJHK75QFi5hn5_zf4/edit?usp=sharing
Make CBCW video at Yellowstone for Upper Sugar social media (8/7/2020).
Train volunteer Chelsea Holman how to conduct CBCW outreach (St. Feriole Slough Landing, Prairie du Chien 8/14/2020).
Write CBCW article for Upper Sugar Oct. Newsletter (9/15/2020).
CBCW Outreach (totals in BOLD):
- Crawford:
  - Ferryville (10017879)
    - 6/28/2020: 0.75 hour, 2 contacts
    - 10/4/2020: 0.25 hour, 0 contacts
    - TOTAL: 1 hour, 2 contacts
  - St. Feriole Slough, Prairie du Chien (10017866)
    - 6/28/2020: 0.75 hours, 29 contacts
    - 7/5/2020: 2 hours, 77 contacts
    - 8/14/2020: 4 hours, 51 contacts
    - 10/3/2020: 4 hours, 7 contacts
    - 10/3/2020: 1.5 hours, 2 contacts
    - TOTAL: 12.25 hours, 163 contacts
  - Ambro Slough (10017878)
    - 10/3/2020: 1 hour, 0 contacts
  - Ambro Access (10017900)
    - 10/3/2020: 0.5 hours, 3 contacts
  - Greenmore Lake Access at Ambro Road (10047642)
    - 10/3/2020: 0.5 hours, 0 contacts
  - Campion Landing (10017845)
    - 10/3/2020: 1.5 hours, 5 contacts
  - Winneshiek Slough Landing (10017502)
    - 10/4/2020: 2.5 hours, 5 contacts
  - Kickapoo River Station 1 – 1962 Boat Landing in Wauzeka (10013664)
    - 10/4/2020: 0.25 hours, 0 contacts
- Richland: N/A
- Sauk:
  - Lake WI-Access- Moon Valley Landing
    - 6/12/2020: 6.5 hours, 54 contacts
    - 7/3/2020: 3 hours, 70 contacts
    - 7/24/2020: 2.5 hours, 21 contacts
    - 8/21/2020: 1.5 hours, 5 contacts
    - TOTAL: 13.5 hours, 150 contacts
- Vernon:
  - Bad Axe River/Mississippi River (10017465)
    - 6/28/2020: 2.25 hours, 6 contacts
  - Blackhawk Upper Access (Near De Soto) (10017872)
    - 6/28/2020: 1.5 hours, 34 contacts
    - 8/14/2020: 2 hours, 18 contacts
    - 10/4/2020: 2.25 hours, 20 contacts
    - TOTAL: 5.75 hours, 72 contacts
  - Hunter’s Point Landing (10017952)
    - 10/9/2020: 4 hours, 6 contacts
  - Upper Hunter’s Point Landing (no Station ID)
    - 10/9/2020: 4 hours, 2 contacts
- Dane:
  - Wisconsin River --Mazo Town Boat Landing (10017374)
    - 10/21/2020: 2 hours, 1 contact
    - 10/22/2020: 1 hour, 0 contacts
    - TOTAL: 3 hours, 1 contact
- Grant:
  - Cassville Public Access (10017587)
    - 6/28/2020: 0.5 hours, 19 contacts
    - 7/5/2020: 2 hours, 25 contacts
    - TOTAL: 2.5 hours, 44 contacts
  - WI River-Boscobel (West)-Von Haden (10017799)
    - 10/4/2020: 0.5 hours, 0 contacts
- Green: N/A
  Iowa:
  - Blackhawk Lake-Access (10018029)
    - 6/13/2020: 4 hours, 32 contacts
    - 7/17/2020: 5 hours, 30 contacts
    - 8/27/2020: 4.5 hours, 12 contacts
    - TOTAL: 13.5 hours, 74 contacts
  - Avoca Lake-Landing (10017427)
    - 10/4/2020: 0.5 hours, 0 contacts
- Lafayette:
  - Yellowstone Lake-Access Near Beach (10017504)
    - 6/4/2020: 1 hour, 6 contacts
    - 6/5/2020: 8 hours, 35 contacts
    - 7/10/2020: 5 hours, 27 contacts
    - 8/7//2020: 4 hours, 25 contacts
    - 9/4/2020: 3.5 hours, 11 contacts
    - Total: 21.5 hours, 104 hours
Grand Total: 90.5 hours (49 North, 41.5 South), 637 contacts (414 North, 223 South)

Activity 2B: ESTABLISH PARTNERSHIPS WITH LOCAL LAW ENFORCEMENT

Local law enforcement training

N/A

Goal 3: MONITOR, IMPLEMENT MANAGEMENT PLANS, AIS CONTROL

Activity 3A: TRAIN, MONITOR, VOUCHER, REPORT

Snapshot Day

Method: Take part in the statewide Snapshot Day monitoring event in partnership with River Alliance.
Deliverable: Site Leader for Snapshot Day site (Viroqua), evaluate three sites with volunteer.
Timeline: May- August
Counties: Vernon

Scout sites for snapshot day (6/26/2020). Look at OLD # sites, 13 total:
https://docs.google.com/spreadsheets/d/1HeRSoclQTTQP9lercP_E-ry1-l_IcRWsgFTDA9CgzAc/edit#gid=0 and photos: https://drive.google.com/drive/folders/1g0rrStT54VJZS57sWutyxDtgAKKezmHM?usp=sharing
(at some point before this, I planned which sites to go to)
Planning for Snapshot Day: confirming sites, starting logistics and communications (716/2020); go through Snapshot Day site leader instructions, Zoom meeting with Jaclyn Lucas of River Alliance for tips and instructions on being a site leader (7/23/2020); make Snapshot Day site maps, organizing supplies box and making kits, read through manual (8/5/2020):
Site Leader Manual: https://docs.google.com/document/d/1n0IirA2FMEaPt6FnPZWeDa7_FRMpReKaIb4XtgqiFjM/edit?usp=sharing
Site Maps: https://docs.google.com/document/d/1SsEtllQQkIjIuhNmifyHFIcDkuKRQjjmxj19PPdnzak/edit
Attend Snapshot Day Volunteer Virtual Training (8/6/2020).
Communicate with Snapshot Day volunteers to inform them of meeting location, supplies, COVID-19 safety procedures, etc. (8/13/2020).
Lead and participate in Snapshot Day. Three sites evaluated, Station IDs: 633199, 10013076, and 10013772 (Sites # 1-3 in spreadsheet) (8/15/2020).
Verify Snapshot Day finds, curly-leaf pondweed, with Alex Selle, DNR AIS Coordinator (8/18/2020).

Clean Lakes Monitoring Network (CLMN)

Method: Volunteers for early detection monitoring will be trained and deployed through Project RED or WDNR CLMN protocols.
Deliverable: Trained early detection volunteers will monitor lakes or rivers for pioneer populations of AIS in Lake Belle View and Sugar River.
Timeline: Sometime during Fieldwork Season (June-Oct 2020)
Counties: Vernon, Dane

Attend and assisted Project RED training at Belleville Community Park with Matt and two volunteers: Jon Beers and Walt Cook (6/17/2020)
Project RED monitoring at ‘Snapshot day Sites North 2020’, AIS samples noted in document with sites (13 sites) (6/26/2020); link to site list: https://docs.google.com/spreadsheets/d/1HeRSoclQTTQP9lercP_E-ry1-l_IcRWsgFTDA9CgzAc/edit?usp=sharing

Monitor for AIS

Method: Frequently monitor water bodies for new or expanding populations of AIS.
Deliverable: Report AIS populations (or lack thereof) in SWIMS. AIS Coordinator will verify populations.
Timeline: Fieldwork Season (June-Oct 2020)
Counties: Crawford, Vernon, Sauk, Grant, Lafayette, Iowa, Dane, Green

Training with Matt to search for and identify non-native vs. native phragmites in Green (Monticello, Monroe) and Lafayette County (Arglye) (6/4/2020).
Inspecting Tiedmanns Pond (Middleton) for goldfish/koi (6/10/2020).
Attend and assisted Project RED training at Belleville Community Park with Matt and two volunteers: Jon Beers and Walt Cook (6/17/2020).
Collecting phragmites in Monroe (6/17/2020).
Scout sites for snapshot day (6/26/2020). Look at OLD # sites, 13 total; link to site list:
https://docs.google.com/spreadsheets/d/1HeRSoclQTTQP9lercP_E-ry1l_IcRWsgFTDA9CgzAc/edit?usp=sharing and link to images: https://drive.google.com/drive/folders/1g0rrStT54VJZS57sWutyxDtgAKKezmHM?usp=sharing
Verify Snapshot Day finds, curly-leaf pondweed, with Alex Selle, DNR AIS Coordinator (8/18/2020).
Inspecting Yellowstone sites (sites 2-7 in Yellowstone Area folder) for PLS and signs of beetle presence (8/7/2020), then sending images to Shelby Adler, WDNR Water Resources Mgmt Spec-Sen (AIS Coordinator) for verification (8/25/2020):
- Station 10051317: 42.769217, -89.925537 (Site 2)
- Station 10054160: 42.762141, -89.923739 (Site 3)
- Station 10054161: 42.759064, -89.952106 (Site 4)
- Station 10050829: 42.760634, -89.952040 (Site 5)
- Station 10054162 : 42.762194, -89.952910 (Site 6)
- (just west of) Station 10017504 : 42.769041, -89.973003 (Site 7)
Link to images:
https://drive.google.com/drive/folders/10QdVB0xtZIaSnbq1XZWnPy6ykN8ZPOVU?usp=sharing
Search for PLS in Iowa Co. in which can use for biocontrol: Ridgeway Pine Relict State Natural Area (confirmed population at Arena Landing (9/24/2020), link to images:
https://drive.google.com/drive/folders/10wS5J1YzHhnk-qyO2dsLVSUcca-KuGXt?usp=sharing
Search for PLS in Iowa Co. in which can use for biocontrol: Blue Mound State Park, Barneveld Prairie State Natural Area, Birch Lake Park, Blackhawk Lake Recreation Area (9/25/2020).
Send photos of AIS from Ferryville Landing and Blackhawk Park to DNR AIS Coordinators Shelby Adler and Alex Selle for verification (10/5/2020).

Rapid Response

Method: Implement the WDNR’s Rapid Response towards Red Swamp Crayfish on Wisconsin River.
Deliverable: Trap for Red Swap crayfish on WI River four different times, no Red Swamp to report.
Timeline: July - Sept
Counties: Sauk

Looked for crayfish at Sauk Canoe Access dump site with Matt (6/10/2020)
Literature to learn crayfish monitoring protocols (6/25/2020)
Received Crayfish monitoring training from Shelby Adler (7/3/2020)
Trap at 3 locations on WI River: Honey Creek – near confluence with Wisconsin River (10052941), Sauk Canoe Access (10019843), and Arena Landing Canoe Launch (10047683) 4 separate times throughout summer:
- Set 7/2/2020, retrieve 7/3/2020 (trapped one native virile crayfish)
- Set 7/23/2020, retrieve 7/24/2020 (no crayfish trapped)
- Set 8/20/2020, retrieve 8/21/2020 (no crayfish trapped)
- Set 9/17/2020, retrieve 9/18/2020 (no crayfish trapped)
Link to images: https://drive.google.com/drive/folders/10MvyYX1mPljGjmGZWAt6ATvQG_SZJ0Qj?usp=sharing
Attend and present RSCF Rapid Response at Lakes and Rivers Partnership Meeting (9/1/2020).

Activity 3B: IMPLEMENT MANAGEMENT PLANS IN THE TARGETED PRIORITIZED WATERSHED

AIS Management Plans

Focus: West Branch Pecatonica AIS Management Plan by WDNR in 2018. The plan addresses four high-priority AIS (Japanese hop and knotweed, non-native phragmites, purple loosestrife) and one pioneer AIS (New Zealand mudsnail).

Method: Identify landowners to participate in West Branch Pecatonica AIS Management Plan.
Deliverable: Collect contact information for landowners to participate in West Branch Pecatonica AIS Management Plan.
Timeline: August and September
Counties: Vernon

Condensed landowner analysis data to identify properties (six total) with the four high-priority AIS: Japanese hop and knotweed, non-native phragmites, purple loosestrife and pioneer AIS: New Zealand mudsnail (in Excel sheet) (7/16,24/2020).
Identified landowner name and contact information (8/6/2020).
Using grant information, drafted letter to landowners to ask for their participation in West Branch Pecatonica AIS Management Plan (8/19-20/2020):
https://docs.google.com/document/d/15SDIFQO82hRWXFRqeVJmKHT1T383EtTakBCBVZ3Byjo/edit?usp=sharing

Funding sources

N/A

Activity 3C: WORK WITH ORGANIZATIONS TO IMPLEMENT BIOCONTROLS AND ENCOURAGE LAKE MANAGEMENT PLANNING GRANT

Partners: Friends of Yellowstone Lake State Park, Friends of Cadiz Park, Friends of the Platte River, and UW Platteville students

Manual removal and biocontrol projects

Method: Monitor for beetles and purple loosestrife populations that could use biocontrol.
Deliverable: Invasive Purple Loosestrife Seedhead Removal Workday.
Timeline: Fieldwork Season (June-Oct 2020)
Counties: Iowa, Lafayette

Inspecting Yellowstone sites for PLS and signs of beetle presence (8/7/2020), then sending images to Shelby Adler, WDNR Water Resources Mgmt Spec-Sen (AIS Coordinator) for verification (8/25/2020); link to images:
https://drive.google.com/drive/folders/10QdVB0xtZIaSnbq1XZWnPy6ykN8ZPOVU?usp=sharing
Search for PLS in Iowa Co. in which can use for biocontrol: Ridgeway Pine Relict State Natural Area (confirmed population at Arena Landing (9/24/2020); link to images:
https://drive.google.com/drive/folders/10wS5J1YzHhnk-qyO2dsLVSUcca-KuGXt?usp=sharing
Search for PLS in Iowa Co. in which can use for biocontrol: Blue Mound State Park, Barneveld Prairie State Natural Area, Birch Lake Park, Blackhawk Lake Recreation Area (9/25/2020).
Invasive Purple Loosestrife Seedhead Removal Workday @ Belleville Community Park (10/23/2020):
https://uppersugar.org/events/invasive-purple-loosestrife-seedhead-removal-workday/

Lake management planning grants

N/A

Selected partnership and planning activities

AIS Trainer Webinar via Zoom with Erin McFarlane, 2 hours (5/27/2020)
Lakes Partnership Aquatic Plant ID workshop via Zoom, 4 hours (6/24,26/2020)
SWIMS training with Matt (7/2/2020)
Attend and present RSCF Rapid Response at Lakes and Rivers Partnership Meeting (9/1/2020)
Send Paige, Upper Sugar Social Media Intern, photos and videos of RSCF Rapid Response, Bait Campaign, OIT, CBCW, Snapshot Day, WFH, etc. for USRWA social media updates throughout fieldwork season).
Attend USRWA weekly Staff Call on occasions.
Adding photos of projects to Shared USRWA Drive (throughout fieldwork season).
- Link to photos of landings along Mississippi:
- https://drive.google.com/drive/folders/1-VbeA-ntKY1aS6lwkUotfV-YEbkcETFk?usp=sharing
End of year report (this document) (10/14-15,19, 22/2020).