## Budget
10-YEAR PRESERVE MANAGEMENT PLAN
MANAGEMENT AREA AND TASK | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
Wetland Zone 1
Develop Management Plan
Fire Breaks (N of creek; around house) (Fall)
Herbaceous Invasive Species Removal
Woody Invasive Species Removal
Wetland Zone 2
Fire Break (Fall) |  |  |  | 562.5 | 1125
Prescribed Fire (Spring) | [5 empty] | BURNED
Monitor Ditch Plug (1) Annually
Meander and Create Species List
Wetland Zone 3
Develop Management Plan
Monitor Ditch Plugs Annually (2) |  |  |  | $566.66 - Repair
Hand Remove Woody Invasive Species
Mow Giant Ragweed
Upland Prairie Zone 1 - 1 Mngmt Zone
Burn Unit 1
Fire Breaks (Fall) |  |  | 850 |  |  | REST | FIREBREAK |  |  |  |  | FIREBREAK
Prescribed Fire (Spring) |  |  | 2490 |  |  |  |  | BURN |  |  |  |  | BURN
Drop female cottonwood tree | [5 empty] | 1280
Spot Herbicide Application - Saplings | [5 empty] | 3250
Upland Prairie Zone 2 - 3 Mngmt Zones
Burn Unit 2A
Fire Breaks (Fall) |  |  |  | 1350 |  | REST |  | FIREBREAK |  |  |  |  | FIREBREAK
Prescribed Fire (Spring) |  |  |  | BURNED $2500 |  |  | REST |  | BURN |  |  |  |  | BURN
Survey Property Boundary | [5 empty] | 1860
Seed Collection
Remove Oldest & Encroaching Willow Saplings
Remove Invasive Species & Odd Trees (shattercane, thistles, etc)
Burn Unit 2B
Fire Breaks (Fall) |  | 400 |  | 400 | 800 | REST | REST |  | FIREBREAK |  |  |  |  | FIREBREAK
Prescribed Fire (Spring) | [5 empty] | 2500 |  |  |  | BURN |  |  |  |  | BURN
Seed Collection
Remove Encroaching Willow Saplings
Remove Invasive Species (shattercane, thistles, etc)
Burn Unit 2C
Fire Breaks (Fall) |  |  |  | 562.5 |  | REST |  |  |  | FIREBREAK |  |  |  |  | FIREBREAK
Prescribed Fire (Spring) | [6 empty] | REST |  |  |  | BURN |  |  |  |  | BURN
Seed Collection
Remove Invasive Species (shattercane, thistles, etc)
Upland Prairie Zone 3 - 1 Mngmt Zone
Burn Unit 3
Fire Breaks (Fall)
Prescribed Fire (Spring)
Seed Collection
Remove Invasive Species (shattercane, thistles, etc)
Restoration Work
Woodland 1
Spot Herbicide Application
Seed Forest Floor with Herbaceous Species (Fall) |  |  |  |  | Indian grass and aster seeds
Herbaceous Invasive Species Removal | [5 empty] | GM
Woody Invasive Species Removal |  |  |  |  | Bkth
Woodland Zone 2
Survey Property Boundary
Woodland Zone 3 - 5 Management Zones
Zone A
Spot Herbicide Application on Cut Buckthorn (Fall) |  | 4639.46 | 1171.52 | 2490
Stewardship Work
Herbaceous Invasive Species Removal | [5 empty] | GM, DR, RCG
Woody Invasive Species Removal
Zone B
Spot Herbicide Application on Cut Buckthorn (Fall)
Herbaceous Invasive Species Removal | [5 empty] | GM, DR
Woody Invasive Species Removal
Zone C
Spot Herbicide Application on Cut Buckthorn (Fall)
Herbaceous Invasive Species Removal | [5 empty] | GM, DR
Woody Invasive Species Removal
Zone D
Spot Herbicide Application on Cut Buckthorn (Fall)
Herbaceous Invasive Species Removal | [5 empty] | GM, DR
Woody Invasive Species Removal
Zone E
Spot Herbicide Application on Cut Buckthorn (Fall)
Herbaceous Invasive Species Removal | [5 empty] | GM, DR
Woody Invasive Species Removal
All Zones
Tree Drop Efforts (if needed) |  | 1300 |  |  |  | 1900
Firewood Collection Event
Public Access Improvements
Mowing Trails and Maintenance |  | 1325 | 860 | 1345 | 2070 | 1395
Parking Lot Plowing
Welcome Sign and Kiosk Upkeep
Educational Kiosks Upkeep | [5 empty] | 79.97 | Assess | Assess | Assess | Assess | Assess | Assess | Assess | Assess | Assess | Possible Replacement
Educational Kiosk Development and Installation
Maintenance of Observation Deck | [11 empty] | Assess | Assess | Assess | Assess | Assess
Maintenance of Boardwalk |  |  |  | 50
Maintenance of Bluebird Nest Boxes Along Trail
Maintenance of Wood Duck Boxes
Miscellaneous |  | $560 - Mike Sabella Rock $682.16 - Boundary Posts Install |  | $66.94 - Dog Station Bags |  | 496.04
Amount Spent | 0 | 8906.62 | 5371.52 | 9893.6 | 3995 | 12761.01 | 0 | 0
Budgeted |  | 12175 | 15250 | 15250 | 6000 | 9000
BUDGET TIMELINE KEY
In Kind Donation | [5 empty] | 2795.31 | observation deck
Management Zones
Volunteer Work
Previous Year's Work
GM = garlic mustard
RCG = reed canary grass
DM = dame's rocket
Bkthrn = buckthorn

## Tracking Progress
10-YEAR PRESERVE MANAGEMENT PLAN
MANAGEMENT AREA AND TASK | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
Wetland Zone 1
Develop Management Plan
Fire Breaks (N of creek; around house) (Fall)
Herbaceous Invasive Species Removal
Woody Invasive Species Removal
Wetland Zone 2
Fire Break (Fall) |  |  |  | 562.5 | 1125 |  | 1500
Prescribed Fire (Spring) | [5 empty] | BURNED | 2000
Monitor Ditch Plug (1) Annually
Meander and Create Species List
Wetland Zone 3
Develop Management Plan
Monitor Ditch Plugs Annually (2) |  |  |  | $566.66 - Repair
Hand Remove Woody Invasive Species
Mow Giant Ragweed | [5 empty] | GGI, GB, LP - REMOVED HEADS OF SHATTERCANE. WEED WHIPPED GIANT RAGWEED
Upland Prairie Zone 1 - 1 Mngmt Zone
Burn Unit 1
Fire Breaks (Fall) |  |  | 850 |  |  | REST | FIREBREAK |  |  |  |  | FIREBREAK
Prescribed Fire (Spring) |  |  | 2490 |  |  |  |  | BURN |  |  |  |  | BURN
Girdle Female Cottonwood Tree | [6 empty] | 600
Spot Herbicide Application - Saplings | [5 empty] | FALL 2021 | 3000
Upland Prairie Zone 2 - 3 Mngmt Zones
Burn Unit 2A
Fire Breaks (Fall) |  |  |  | 1350 |  | REST |  | FIREBREAK |  |  |  |  | FIREBREAK
Prescribed Fire (Spring) |  |  |  | 2500 |  |  | REST |  | BURN |  |  |  |  | BURN
Seed Collection
Remove Oldest & Encroaching Willow Saplings | [5 empty] | 1. GGI, GB, LP - FLAGGED ALL SMALL SAPLINGS TO BE CUT. 2.GGI, GB - JULY 2021, REMOVED SAPLINGS ALONG TRAIL, 20 FEET EAST OF WETLAND BURN KIOSK.
Remove Invasive Species & Odd Trees (shattercane, thistles, etc)
Burn Unit 2B
Fire Breaks (Fall) |  | 400 |  | 400 | 800 | REST | REST |  | FIREBREAK |  |  |  |  | FIREBREAK
Prescribed Fire (Spring) | [5 empty] | BURNED |  |  |  | BURN |  |  |  |  | BURN
Seed Collection
Remove Encroaching Willow Saplings
Remove Invasive Species (shattercane, thistles, etc)
Burn Unit 2C
Fire Breaks (Fall) |  |  |  | 562.5 |  | REST |  |  |  | FIREBREAK |  |  |  |  | FIREBREAK
Prescribed Fire (Spring) | [5 empty] | 2500 | REST |  |  |  | BURN |  |  |  |  | BURN
Seed Collection
Remove Invasive Species (shattercane, thistles, etc) | [5 empty] | 1. REMOVED SEED HEADS FROM ALL ENCROACHING REED CANARY GRASS FROM WETLAND 2
Upland Prairie Zone 3 - 1 Mngmt Zone
Burn Unit 3
Fire Breaks (Fall)
Prescribed Fire (Spring)
Seed Collection
Remove Invasive Species (shattercane, thistles, etc)
Restoration Work
Woodland 1
Spot Herbicide Application
Seed Forest Floor with Herbaceous Species (Fall) |  |  |  |  | Indian grass and aster seeds
Herbaceous Invasive Species Removal | [5 empty] | GM
Woody Invasive Species Removal |  |  |  |  | Bkth
Woodland Zone 2
Survey Property Boundary
Woodland Zone 3 - 5 Management Zones
Zone A
Spot Herbicide Application on Cut Buckthorn (Fall) |  | 4639.46 | 1171.52 | 2490
Stewardship Work
Herbaceous Invasive Species Removal | [5 empty] | GM, DR, RCG
Woody Invasive Species Removal
Zone B
Spot Herbicide Application on Cut Buckthorn (Fall)
Herbaceous Invasive Species Removal | [5 empty] | GM, DR
Woody Invasive Species Removal
Zone C
Spot Herbicide Application on Cut Buckthorn (Fall)
Herbaceous Invasive Species Removal | [5 empty] | GM, DR
Woody Invasive Species Removal
Zone D
Spot Herbicide Application on Cut Buckthorn (Fall)
Herbaceous Invasive Species Removal | [5 empty] | GM, DR
Woody Invasive Species Removal
Zone E
Spot Herbicide Application on Cut Buckthorn (Fall)
Herbaceous Invasive Species Removal | [5 empty] | GM, DR
Woody Invasive Species Removal
All Zones
Tree Drop Efforts (if needed) |  | 1300 |  |  |  | 1900
Firewood Collection Event
Public Access Improvements
Mowing Trails and Maintenance |  | 1325 | 860 | 1345 | 2070 | 1766 | 1500
Parking Lot Plowing
Welcome Sign and Kiosk Upkeep
Educational Kiosks Upkeep | [5 empty] | Assess | Assess | Assess | Assess | Assess | Assess | Assess | Assess | Assess | Assess | Possible Replacement
Educational Kiosk Development and Installation
Maintenance of Observation Deck | [5 empty] | 2795.31 | [5 empty] | Assess | Assess | Assess | Assess | Assess
Maintenance of Boardwalk |  |  |  | 50
Maintenance of Bluebird Nest Boxes Along Trail
Maintenance of Wood Duck Boxes
Miscellaneous |  | $560 - Mike Sabella Rock $682.16 - Boundary Posts Install |  | $66.94 - Dog Station Bags
Amount Spent | 0 | 8906.62 | 5371.52 | 8368.6 | 3995 | 8961.31 | 8600 | 0
Budgeted |  | 12175 | 15250 | 15250 | 6000 | 9000 | 10000
BUDGET TIMELINE KEY
In Kind Donation
Management Zones
Volunteer Work
Previous Year's Work
GM = garlic mustard
RCG = reed canary grass
DM = dame's rocket
Bkthrn = buckthorn

## Expenses
2020
Observation deck: | 900 | labor
| 1895.31 | materials
Total: | 2795.31
2021
1900 | A1 Tree Service | tree drop in woods
1860 | Combs and Associates | survey work
80 | Awesome Landscaping | mowing
210 | Awesome Landscaping | mowing
496.04 | Geoff | work
2500 | Pheasants Forever | burn
160 | Awesome Landscaping | mowing
160 | Awesome Landscaping | mowing
79.97 | mcmaster carr | acrylic
3250 | ERC | cottonwood saplings
235 | Awesome landscaping | mowing
550 | Awesome Landscaping | mowing
1280 | A1 Tree Service | cottonwood removal
12761.01