GRANT CLOSE-OUT CHECKLIST

BURNETT COUNTY

Burnett County AIS Prevention & Education

AEPP-169-09

Upon completion of project, the sponsor will provide the state with a comprehensive report including:

(1)  Project report/assessment of education/outreach activities including examples of materials

developed, monitoring activities, and data collected, including descriptions of the extent of AIS

in the County, control measure details, prevention & AIS plans, & information in 2-9.

24 May 2010 - Received CBCW Report (paper copy & electronic copy).

29 Jan 2015 – Received Final Report (paper copy & Electronic copy).

Monitoring activities and data included in plant surveys and completed APMs.

Public outreach/education data included in all CBCW trainings, countless presentations,

and two meetings conducted for each APM (kick-off & wrap-up/approval).

( 2) Financial Payment Request with documentation of grant administration

time and services and proof of payments for reimbursement.

29 Jan 2015 – Received Final Payment Request.

(2)  Baseline data (species, GPS locations, estimated infestation size) & GIS maps of EWM,

purple loosestrife, & AIS populations.

24 May 2010 - AIS monitoring was carried out by boat surveillance/grab sample on several lakes.  There were no new AIS infestations discovered through this monitoring with the exception of small purple loosestrife beds on Fish Lake and curly leaf pondweed on Benoit Lake.  Report provides general description of CLP bed in Benoit Lake.  Map or density report not provided.  Map included in report indicating location of purple loosestrife populations and locations of beetle releases.  In addition to this monitoring, EWM was discovered on Little Trade Lake in June and verified by the DNR in July 2009.  There is no map in the report.

29 Jan 2015 -  Final Report includes a Purple Loosestrife Control report which contains maps for  purple loosestrife locations.

The EWM on Little Trade Lake was mapped by Polk County Land & Water and incorporated as part of the APM done for that lake association.

The Curly Leaf Pondweed on Benoit Lake was identified prior to the beginning of this grant, and to date, Burnett County still has not received verification of those vouchers; hence without a valid identification the locations were not mapped.  Burnett County will revisit Benoit Lake in 2015 and resubmit any findings.

(3)  Aquatic plant survey results (i.e. point intercept method).

24 May 2010 -  Report does not include data on point intercept studies nor reference any completed.

29 Jan 2015 –  Final Report contains Excel spreadsheets  and supporting documents for each plant

survey (electric copy).  All maps and survey results are included with their respective

APM.

(4)  Purple Loosestrife release site locations and management summary.

Map included in report indicating location of purple loosestrife populations and

locations of beetle releases.

Page 1 0f 2

(5)  CBCW summary. Data to include lake contacts, monitors, volunteers, presentations, etc.

CBCW data entered into SWIMS database.  Report describes inspectors, contacts, results of

inspections and contacts.  In addition, a special inspector was hired for Trade

Lake/Little Trade Lake due to the newly discovered EWM.  Descriptions of these

inspections and results were also included.

29 Jan 2015 – Final Report includes annual progress reports providing summaries of CBCW data.

(76)  County-wide resource list, including contacts, monitors, volunteers, presentations, etc.

29 Jan 2015 – All contact information is included on the CD.  The trainees/volunteers are listed on

attendance sheets.  Resource contacts are mainly listed on newsletters.

(7)  APM Plans

29 Jan 2015 – Received six APM Plans (paper copy & electronic copy).

(8)  Waterfront property owner packet.

This packet is no longer produced.  It proved too costly to continue.

Since then, much of the same information was moved to the website.

(9)  Countywide AIS prevention & control strategy.

Per direction from Pamela Toshner, Burnett Co LWCD was told this report was not necessary as it was not required by the grant – nor was it listed as a deliverable on the final grant contract.  However, St Croix River Association (which Burnett Co LWCD is a part) is working on a prevention & control strategy that will cover the St Croix basin.   Dave Ferris is actively involved in this plan development at this time.

APPROVED FOR PAYMENT

___________________________________  Date _________

Page 2 0f 2