Water Quality Monitoring

Special Project Workplan Proposal - FY 2007

GENERAL INFORMATION

Author Name:	Jim Amrhein			Telephone:  275-3280

Region: SCR					Program:  WT

Basin: GPSP

PROJECT INFORMATION

Project Category: 1				Activity Code:	 WTTM-02

Project Location(s): Honey Creek and tributaries

Watershed(s):  Honey and Richland Creeks

County or Counties:  Green

WORKPLAN DETAILS

1. Project Description (including what, when, where, who of project):

What:	Monitor Honey Creek for habitat impairment caused by sedimentation.  Conduct fisheries IBI and habitat assessment Honey Creek (3 sites) and one site on each of 3 major tributaries.  Conduct monthly nutrient analysis (12) of Honey Creek below WWTP outfall.  Conduct watershed assessment to determine sediment sources.  Conduct macroinvertebrate analysis at 6 sites.

When:	July 06-June 07

Where: Honey Creek (3 sites); Whitehead Creek; Spring Creek; Hawthorne Creek

Who:	Jim Amrhein – Water Resources Specialist

2. Justification (why is this project necessary?):

Need to complete a TMDL on the habitat impairment which is the reason the stream is on the 303(d) list.  This was one of the five regional projects submitted for TMDLs as required.  This project will hopefully result in corrective management actions.

3. Performance Measure(s) (including sample collection, report completion date, etc.):

- Fisheries IBIs and habitat indices will be taken at 3 sites (to complement the 3 sites already assessed) as well as 1 site on each of 3 major tributaries to determine contemporary status and biological potential.

- Macroinvertebrate samples (3 sites on Honey Creek and 1 on each of 3 major tributaries).

- Nutrient samples downstream from the Monroe Sewerage Treatment Plant to determine if nutrient loading and resulting algal growth is affecting habitat and biota.

- Report summarizing findings to be completed by March, 2008

4. Data Storage System (work station computer, lab portal, SWIMS, FH database, etc.):

- Fish IBI and habitat assessment will be stored in the FH database

- Nutrient data will be accessible through the SLOH portal

- Water Chemistry (Sonde) data and watershed narrative information will be captured on SWIMS

5. File Manager Responsible for Data Entry:  Jim Amrhein

| Water Quality Special Project Workplan Proposal |  |  |
| --- | --- | --- |
| #### Cost Worksheet |  |  |
| ### FY 2007 |  |  |
| July 1, 2006 - June 30, 2007 |  |  |
|  | Hours | Cost ($) |
| FTE Resources | 80 |  |
| LTE Resources | 100 | 1500 |
| Line S (supplies, contracts, travel) |  | $150 $690 (bugs) |
| SLOH Lab Services (attach lab spreadsheet) |  | 1613.64 |
| Equipment <$5,000 |  |  |
| Capital Equipment =>$5,000 |  |  |
| Subtotal DNR contributions |  |  |
| Partner Contributions |  |  |
| Total Contributions |  | 3953.64 |