Water Quality Monitoring

Special Project Workplan Proposal - FY 2007

GENERAL INFORMATION

Author Name:  	Jim Cahow			Telephone:	715/637-6863

Region:   NOR					Program:  WT

Basin:   St Croix

PROJECT INFORMATION

Project Category:	2

Activity Code:	 WTSK

Project Location(s):  Chetek River

Watershed(s):  Red Cedar River (Chippewa Basin)

County or Counties:  Barron

WORKPLAN DETAILS

1. Project Description (including what, when, where, who of project):

Jim Cahow will:

- conduct diurnal D.O. and temperature monitoring on the Chetek River  between Hwy 53 and its confluence with the Red Cedar River to determine the frequency and duration of standards violations below the 3mg/l D.O. standard during late July and August.

- Collect weekly blue green algae samples on the Chetek River near the campground on the west side of Hwy 53 to document species present as well as density and toxin production if problem blooms merit closer scrutiny July 15th to August 30th.

- Collect weekly water chemistry samples at least 4 out of the 6 weeks when problem bloom periods occur to assess contributions of suspended solids, B.O.D., Total Phosphorus, Nitrate+Nitrite, Total kjeldahl – N, Ammonia July 15th to August 30th   from the Chetek Chain of Lakes to the Chetek River.

2. Justification (why is this project necessary?):

It is necessary to properly document the kind and severity of the limiting factors which may be keeping the Chetek River and downstream receiving waters from meeting their full biological potential as required by the clean water act.

These efforts also mesh closely with at least one of the four main goals identified within the Department’s Strategic Plan (Goal #2 Sustaining Ecosystems) and also closely meshes with at least 2 of the 4 main goals for the Water Division (Goal #1;To protect the waters of the state that are held in trust for all people of the state through enforcement of the public trust doctrine & Goal #2 to fully implement the Clean Water Act in order insure a water body is meeting its full biological potential including Endangered, Threatened, and Rare species which are often intolerant of pollution and low D.O.).

3. Performance Measure(s) (including sample collection, report completion date, etc.):

Collect weekly water chemistry samples and conduct continuous D.O. monitoring during the period when aquatic plants are senescing within the Chetek Chain of Lakes and nutrients released from tissues begin to drive dangerous blue green algae blooms which can be concentrated in flows over the dam depending upon wind direction.  These contributions are likely the dominate limiting factor for the Chetek River and are likely to still exert a strong influence on the Red Cedar River (one of the states best warm water riverine fisheries).

A report will be completed summarizing annual data interpretation and recommended future monitoring and potential management implications to insure the Chetek River is fully meeting its biological potential.

4. Data Storage System (work station computer, lab portal, SWIMS, FH database, etc.):

1.  Lab data will be available through the lab portal

2. Continuous D.O. and temp data will be integrated into the continuous monitoring data set.

5. File Manager Responsible for Data Entry:

Jim Cahow will insure that all data is forwarded to the appropriate staff to get entered into the appropriate databases.

| Water Quality Special Project Workplan Proposal |  |
| --- | --- |
| Cost Worksheet |
| FY 2007 |  |  |
| July 1, 2006 - June 30, 2007 |  |  |
|  | Units/Hours | Cost ($) |
| FTE Resources | 60 hrs |  |
| LTE Resources | 40 hrs | $750 |
| Line S (supplies, contracts, travel) | Mileage = 600 Meals = 12 lunches | Mileage = $200 Meals = $60 |
| SLOH Lab Services (attach lab spreadsheet) | 4 weekly sampling events | $622.66 |
| Equipment <$5,000 | 2 data sondes | $4800 |
| Capital Equipment =>$5,000 |  |  |
| Subtotal DNR contributions |  |  |
| Partner Contributions |  |  |
| Total Contributions |  | $5683 |