## Project Description
PLEASE FILL IN THE BLUE HIGHLIGHTED CELLS USE TABS BELOW TO SWITCH BETWEEN WORKSHEETS |  |  | July 1, 2007 - June 30, 2008
1. PROJECT AUTHOR
a) | Author Name: | Jim Cahow
b) | Region: | NOR
c) | Telephone: | 715-637-6863
d) | Program: | wt
e) | Supervisor's Name: | Kathy Bartilson
2. PROJECT CATEGORY (1, 2a, 2b, 2c, 3a, 3b, 3c) |  | 1 or 2c
3. ACTIVITY CODE |  | WTSK
4. WORKPLAN DETAILS
a) | Project Description: | Upper Red Cedar River Event Sampling and Diurnal DO - Impaired Waters Monitoring
b) | Project Justification:
| 1.Why is project necessary? | Continue data collection from approved 2006 project
| 2. What mgmt. Question is being addressed? | During high runoff events what proportion of the total annual nutrient and sediment loadings or concentrations are coming from land uses in the upper Red Cedar River when compared to those nutrient and sediment loadings or additions coming from the Chetek River during Late July and August when peak Algae blooms and macrophyte senecence on the Chetek Chain of Lakes are believed to be a dominant source in the upper Red Cedar River Basin.
c) | Locational Information:
| 1. Watershed | Upper Red Cedar River - Impaired Waters Monitoring
| 2. County(ies) | Barron
| 3. Water Body(ies) - List All | Red Cedar River and Chetek River
| 3. WBIC(s) - List All | 2063500 & 2089000
d) | Performance Measures:
| 1. # of sample sites | 5
| 2. # of of sampling events. | up to 5; depending on runoff conditions and lab related sample time constraints
| 3. Date sample collection complete. | Ongoing and dependent on getting high runoff events. Status report by June 08
| 4. Date of complete data entry. | 2007-07-08
| 5. Date of final report. | This is a longterm project that seeks to characterize severity and variability within runoff events. Sampling should continue until runoff sample size is adequate to account for variability between samples and provide a crude measure of total loading
e) | Data Management
| 1. What database will be used? | existing DNR databases (SWIMS)
| 2. Who is responsible for entering data? | Jim cahow will insure that the data gets to the approriate people to be enetered - ideally my year round LTE tech.
5. BUDGET
a) | FTE Hours Needed | Up to 80 hours for runoff samples & up to 120 hours for sonde set up and recovery and data management. A summary report will require another 80 hours.
b) | LTE Funds Needed | equipment familiarity - 40 hours, sonde deployment - 120 hours, Data base training and data entry - 60 hours, report prep - 40 hours, assist with runoff samples - 60 hours -
c) | Supplies - Describe in detail. | waders-$80, meals for up to 10 days = $60
d) | Travel | 5 weeks sonde placement, recovery, and maintenance = 750 miles & 5 runoff events sampled = 750 miles
e) | Contractual - Who? What? How Much? | NA
f) | Equipment - What is needed and why? Cost? | Two additional data sondes at approximately $4,000 would help replace old failing equipment and help document loading differences between sites above and below Rice Lake on the upper Red Cedar River. If replacement sondes can not be bought replacement D.O. probes should be ordered for the older YSI 6000's. Replacement D.O. probes are running around $700 each. The monitoring committe also recommended last year that we include pH during our diurnal D.O. and temp monitoring. pH replacement probes for the YSI 6000's are running around $500 each for a total cost of $1000.
g) | Capital Equipment >$5,000 - What is needed and why? Cost? | see Chetek proposal for USGS gauging station request
h) | State Lab of Hygiene Analyses - Describe the number and type of parameters being tested. | 5 runoff related samples will be collected if conditions and timing are appropraite using the following parameters: Suspended Solids, BOD, Chlorides, Total Phosphorus, Nitrate& Nitrite, Total Kjeldahl -N, Ammonia. Additionally a baseflow sample could be collected to establish background concentrations.
i) | Partner Contributions - will others (outside DNR) contribute time and/or money to the project? If yes, describe briefly. | Barron County - will be working with us to control problem sources around the Chetek Chain of Lakes

## Project Budget
PLEASE FILL IN THE YELLOW HIGHLIGHTED CELLS Grey Cells Populate Automatically USE TABS BELOW TO SWITCH BETWEEN WORKSHEETS
Project Budget - State FY 2008
July 1, 2007 - June 30, 2008
1 | FTE Hours | 280
2 | LTE Information |  | Computed LTE Salary
| 2a - Hours Needed | 320 | 5457.7523
| 2b - Hourly Wage | 12
| 2c - Fringe @24.58% of Salary | 3.306
| 2d - Indirect @11.43% of (Salary + Fringe) | 1.7495
3 | Supplies |  | 140
4 | Travel |  | 700
5 | Contractual |  | 0
6 | Equipment <$5,000 |  | 6400
7 | Capital Equipment >$5,000 |  | 0
8 | DNR Contributions: Sub-total: |  | 12697.7523
9 | Partner Contributions |  | 0
10 | SLOH Lab Services* |  | 4938.5
11 | Total Cost of Project |  | 17636.2523
* If requesting SLH support, the attached worksheet must be completed.

## SLOH Worksheet
PLEASE FILL IN THE YELLOW HIGHLIGHTED CELLS Grey Cells Populate Automatically USE TABS BELOW TO SWITCH BETWEEN WORKSHEETS
Basic Agreement Water Quality Monitoring
Collector/Submitter Name: | Jim Cahow
Project Name: | Red Cedar River - Runoff event sampling & Diurnal D.O. studies
Activity Category Name/Code: | Project Category 2c - a Continuation of previously approved special studies
Activity Name/Code: | Surface Water Quality Monitoring - 303d list activities
Project Number*:
Mon. Activity Code: | WTSK
SLOH Acct. Code*: | WT082
FY of Analysis: | FY 2008
* For requests to use the SLOH Basic Aggreement Resources, this form must be completed and submitted for review and approval by______ before samples may be submitted. The Test Request forms must be completed using the appropriate codes or the sample may
Test ID | Test Description | RVU/Test | # of | Total for
|  |  | Samples | Test
Bacti | Price per RVU = | 15.75
B200ALT | MFFCC | 0.8 |  | 0
B152ALT | E COLI ENZYMATIC SUBTRATE QUANTITRAY MPN | 1.5 |  | 0
B210ALT | FECAL STREPTOCOCCI | 0.9 |  | 0
Inorganics | Price per RVU = | 11.9
Nutrients
I440NLD | AMMONIA-N (SM 4500-NH3H) | 2 | 25 | 595
I460MLD | NITRATE PLUS NITRITE-N | 2 | 25 | 595
I470BLT | TOTAL KJELDAHL NITROGEN | 2.1 | 25 | 624.75
I520PLT | TOTAL PHOSPHORUS | 1.5 | 25 | 446.25
I530ALD | ORTHOPHOSPHATE AS P, LOW RANGE | 2.5 |  | 0
Solids
I640FLT | TOTAL SOLIDS | 1.5 |  | 0
I640GLT | TOTAL VOLATILE SOLIDS | 1 |  | 0
I650HLT | SUSPENDED SOLIDS | 1.9 | 25 | 565.25
I650HLT | VOLATILE SUSPENDED SOLIDS | 1 |  | 0
I640FLD + I640FLT | TOTAL DISSOLVED SOLIDS, 180 C, PLUS TOTAL SOLIDS | 3.4 |  | 0
I660ALT | TURBIDITY | 0.9 |  | 0
Misc.
I120ALT | ALKALINITY, GRAN TECHNIQUE | 3 |  | 0
I180ALT | BOD, 5 DAY | 3.7 | 25 | 1100.75
I240ELT | CHLORIDE | 1.5 | 25 | 446.25
I251UNF | CHLOROPHYLL A, FLUORESCENCE, FF (WELSCHMEYER 1994) | 2.3 |  | 0
I251UNL | CHLOROPHYLL A, FLUORESCENCE (WELSCHMEYER 1994) | 2.3 |  | 0
I280ALT | COD,LOW LEVEL | 2 |  | 0
I290ALT | COLOR, TRUE, PT-CO | 1.2 |  | 0
I305ALT | AUTOMATED CONDUCTIVITY, PH & ALKALINITY | 1.9 | 25 | 565.25
I320VUT | CYANIDE | 4 |  | 0
I500ALT | PH, LAB | 0.7 |  | 0
I410BLT | MBAS, COLORIMETRIC | 4.6 |  | 0
I560LLD | SILICA, DISSOLVED, LOW RANGE | 1.7 |  | 0
I600DLT | SULFATE, AUTOMATED | 1.9 |  | 0
I710ALT | FIELD TESTS (Required if field pH, DO, etc. on Lab Slip) | 0.4 |  | 0
Metals
| Hardness (Includes Ca, Mg, & Digestion) | 4 |  | 0
I370IDT | IRON, TOTAL , ICP | 1 |  | 0
I400IDT | MANGANESE, TOTAL , ICP | 1 |  | 0
I540IDT | POTASSIUM, TOTAL , ICP | 1 |  | 0
I580IDT | SODIUM, TOTAL , ICP | 1 |  | 0
I322IDT | DIGESTION, TOTAL , LIQUIDS, ICP + ICP SETUP | 2 | 0 | 0
ICP Panels
| Ca+Mg+Na+Hardness, Total | 3.3 | 0 | 0
| Ca+Mg+Na+Mn+Fe+K+Zn+Hardness, Total | 7.3 | 0 | 0
I322IDT | DIGESTION, TOTAL , LIQUIDS, ICP + ICP SETUP | 2 | 0 | 0
Trace Low Level Metals
I323ZDR | DIG, TOT REC, IN BOTTLE, ICPMS | 1 | 0 | 0
I495PBC | CLEAN BOTTLE PREP | 1.8 | 0 | 0
I860ZUT | ICP-MS 11 TOTAL RECOVERABLE (11.3RV + 0.7RV per element) | 13.7 |  | 0
I430ZDT | Mercury, Atomic Fluorescence, (low level) | 5.3 |  | 0
I495ZBC | Clean Bottle Prep, Hg (low level)(glass) | 1.4 | 0 | 0
Biomonitoring
CHRONIC TEST WITH FATHEAD MINNOW
CHRONIC TEST WITH CERIODAPHNIA d.
CHRONIC TEST WITH DAPHNIA m.
ACUTE TEST WITH FATHEAD MINNOW
ACUTE TEST WITH CERIODAPHNIA d.
ACUTE TEST WITH DAPHNIA m.
ACUTE LOW VOLUME SCREEN
MICROTOX TEST
(Note: Cost for biomonitoring samples funded differently)
|  | SLOH Total = |  | 4938.5