## Project Description
PLEASE FILL IN THE BLUE HIGHLIGHTED CELLS USE TABS BELOW TO SWITCH BETWEEN WORKSHEETS |  |  | July 1, 2007 - June 30, 2008
1. PROJECT AUTHOR
a) | Author Name: | Mark Hazuga - Dan Helsel
b) | Region: | WCR
c) | Telephone: | 715-359-2580 and 715- 284- 1431
d) | Program: | Watershed
e) | Supervisor's Name: | Paul LaLiberte
| Project Name: | Trempealeau River Study
2. PROJECT CATEGORY (1, 2a, 2b, 2c, 3a, 3b, 3c) |  | 1
3. ACTIVITY CODE |  | WTSK
4. WORKPLAN DETAILS
a) | Project Description: | The Trempealeau River at Dodge has been monitored for the past several years as a LTT network site. The median total phosphorus concentration at the site is 369 ug/L which is the highest amoung the 42 LTT sites. Concentrations of bacteria, suspended solids and dissolved silica are amoung the highest of other LTT sites. Very limited biological data has been collected from the river and the extent of high phosphorus concentrations are not known. Another unknown, is the impact the high phosphorus concentrations are indirectly having on the biological community. The Department would like to request funds to evaluate the Trempealeau River including a site on both the North and South Branch Trempealeau Rivers at eight locations for fish, macroinvertebrates, continuous dissolved oxygen, continuous temperature, habitat and water chemistry. Fishery and habitat data would be collected during July or August and macroinvertebrates would be collected in the fall.
b) | Project Justification:
| 1.Why is project necessary? | The Department does not know if the high phosphorus concentrations found at the Dodge LTT site are indicative of the entire stream and if there is an impairment to aquatic life as a result of high phosphorus concentrations. This project will evaluate both water quality and biological conditions to determine if an impairment exists.
| 2. What mgmt. Question is being addressed? | 303 D monitoring
c) | Locational Information:
| 1. Watershed | Lower, Middle and Upper Trempealeau, Elk Crek and Pigeon Creeks Watersheds
| 2. County(ies) | Buffalo, Trempealeau
| 3. Water Body(ies) - List All | Trempealeau River (1769900), Elk Creek (1782500), Pigeon Creek (1792500), NB Trempealeau River (1807200) and SB Trempealeau River(1806900)
| 3. WBIC(s) - List All | see above
d) | Performance Measures:
| 1. # of sample sites | Fish, bugs, water chemistry, continuous DO and habitat will be completed at 8 sites and water chemsitry only will be collected at four tributary sites.
| 2. # of of sampling events. | 1 sampling event for fish, bugs and habitat; 2 one week DO deployments and 2 non event syoptic water chemsitry surveys.
| 3. Date sample collection complete. | June, July, August, September
| 4. Date of complete data entry. | SLOH, Bug results will be direct dump into SWIMMs when analysis is complete. Fish and habitat data will be entered into FH database during winter. Continuous DO data will be uploaded during winter months.
| 5. Date of final report. | 2008-06-01
e) | Data Management
| 1. What database will be used? | SWIMMs, Storet, UW Point Bug Database, FH Database
| 2. Who is responsible for entering data? | Basin Biologist
5. BUDGET
a) | FTE Hours Needed | 300
b) | LTE Funds Needed | 200 LTE Hours X $11 = $2,200
c) | Supplies - Describe in detail. | FTE and LTE Meals = $300
d) | Travel | 150 miles per day x 11 days x .42 = $693
e) | Contractual - Who? What? How Much? | UWSP - Bug contract 8 samples @ 147 = $1176
f) | Equipment - What is needed and why? Cost?
g) | Capital Equipment >$5,000 - What is needed and why? Cost?
h) | State Lab of Hygiene Analyses - Describe the number and type of parameters being tested. | 20 samples analyzed for total phosphorus, dissolved phosphorus, chloraphyll a, suspended solids, volatile suspended solids, BOD, ammonia nitrogen, nitrate -nitrite nitrogen, TKN, E. Coli
i) | Partner Contributions - will others (outside DNR) contribute time and/or money to the project? If yes, describe briefly. | None

## Project Budget
PLEASE FILL IN THE YELLOW HIGHLIGHTED CELLS Grey Cells Populate Automatically USE TABS BELOW TO SWITCH BETWEEN WORKSHEETS
Project Budget - State FY 2008
July 1, 2007 - June 30, 2008
1 | FTE Hours | 300
2 | LTE Information |  | Computed LTE Salary
| 2a - Hours Needed | 200 | 3126.8372
| 2b - Hourly Wage | 11
| 2c - Fringe @24.58% of Salary | 3.0305
| 2d - Indirect @11.43% of (Salary + Fringe) | 1.6037
3 | Supplies |  | 350
4 | Travel |  | 693
5 | Contractual bugs |  | 1176
6 | Equipment <$5,000 |  | 0
7 | Capital Equipment >$5,000 |  | 0
8 | DNR Contributions: Sub-total: |  | 5345.8372
9 | Partner Contributions |  | 0
10 | SLOH Lab Services* |  | 4473.28
11 | Total Cost of Project |  | 9819.1172
* If requesting SLH support, the attached worksheet must be completed.

## SLOH Worksheet
PLEASE FILL IN THE YELLOW HIGHLIGHTED CELLS Grey Cells Populate Automatically USE TABS BELOW TO SWITCH BETWEEN WORKSHEETS
Basic Agreement Water Quality Monitoring
Collector/Submitter Name: | Mark Hazuga and Dan Helsel
Project Name: | Trempealeau River 303 d monitoring
Activity Category Name/Code: | 1
Activity Name/Code: | WTSK
Project Number*:
Mon. Activity Code:
SLOH Acct. Code*:
FY of Analysis: | FY 2008
* For requests to use the SLOH Basic Aggreement Resources, this form must be completed and submitted for review and approval by______ before samples may be submitted. The Test Request forms must be completed using the appropriate codes or the sample may
Test ID | Test Description | RVU/Test | # of | Total for
|  |  | Samples | Test
Bacti | Price per RVU = | 15.75
B200ALT | MFFCC | 0.8 |  | 0
B152ALT | E COLI ENZYMATIC SUBTRATE QUANTITRAY MPN | 1.5 | 20 | 472.5
B210ALT | FECAL STREPTOCOCCI | 0.9 |  | 0
Inorganics | Price per RVU = | 11.9
Nutrients
I440NLD | AMMONIA-N (SM 4500-NH3H) | 2 | 20 | 476
I460MLD | NITRATE PLUS NITRITE-N | 2 | 20 | 476
I470BLT | TOTAL KJELDAHL NITROGEN | 2.1 | 20 | 499.8
I520PLT | TOTAL PHOSPHORUS | 1.5 | 20 | 357
I530ALD | ORTHOPHOSPHATE AS P, LOW RANGE | 2.5 | 20 | 595
Solids
I640FLT | TOTAL SOLIDS | 1.5 |  | 0
I640GLT | TOTAL VOLATILE SOLIDS | 1 |  | 0
I650HLT | SUSPENDED SOLIDS | 1.9 | 20 | 452.2
I650HLT | VOLATILE SUSPENDED SOLIDS | 1 | 20 | 238
I640FLD + I640FLT | TOTAL DISSOLVED SOLIDS, 180 C, PLUS TOTAL SOLIDS | 3.4 |  | 0
I660ALT | TURBIDITY | 0.9 |  | 0
Misc.
I120ALT | ALKALINITY, GRAN TECHNIQUE | 3 |  | 0
I180ALT | BOD, 5 DAY | 3.7 | 6 | 264.18
I240ELT | CHLORIDE | 1.5 |  | 0
I251UNF | CHLOROPHYLL A, FLUORESCENCE, FF (WELSCHMEYER 1994) | 2.3 |  | 0
I251UNL | CHLOROPHYLL A, FLUORESCENCE (WELSCHMEYER 1994) | 2.3 | 20 | 547.4
I280ALT | COD,LOW LEVEL | 2 |  | 0
I290ALT | COLOR, TRUE, PT-CO | 1.2 |  | 0
I305ALT | AUTOMATED CONDUCTIVITY, PH & ALKALINITY | 1.9 |  | 0
I320VUT | CYANIDE | 4 |  | 0
I500ALT | PH, LAB | 0.7 |  | 0
I410BLT | MBAS, COLORIMETRIC | 4.6 |  | 0
I560LLD | SILICA, DISSOLVED, LOW RANGE | 1.7 |  | 0
I600DLT | SULFATE, AUTOMATED | 1.9 |  | 0
I710ALT | FIELD TESTS (Required if field pH, DO, etc. on Lab Slip) | 0.4 | 20 | 95.2
Metals
| Hardness (Includes Ca, Mg, & Digestion) | 4 |  | 0
I370IDT | IRON, TOTAL , ICP | 1 |  | 0
I400IDT | MANGANESE, TOTAL , ICP | 1 |  | 0
I540IDT | POTASSIUM, TOTAL , ICP | 1 |  | 0
I580IDT | SODIUM, TOTAL , ICP | 1 |  | 0
I322IDT | DIGESTION, TOTAL , LIQUIDS, ICP + ICP SETUP | 2 | 0 | 0
ICP Panels
| Ca+Mg+Na+Hardness, Total | 3.3 | 0 | 0
| Ca+Mg+Na+Mn+Fe+K+Zn+Hardness, Total | 7.3 | 0 | 0
I322IDT | DIGESTION, TOTAL , LIQUIDS, ICP + ICP SETUP | 2 | 0 | 0
Trace Low Level Metals
I323ZDR | DIG, TOT REC, IN BOTTLE, ICPMS | 1 | 0 | 0
I495PBC | CLEAN BOTTLE PREP | 1.8 | 0 | 0
I860ZUT | ICP-MS 11 TOTAL RECOVERABLE (11.3RV + 0.7RV per element) | 13.7 |  | 0
I430ZDT | Mercury, Atomic Fluorescence, (low level) | 5.3 |  | 0
I495ZBC | Clean Bottle Prep, Hg (low level)(glass) | 1.4 | 0 | 0
Biomonitoring
CHRONIC TEST WITH FATHEAD MINNOW
CHRONIC TEST WITH CERIODAPHNIA d.
CHRONIC TEST WITH DAPHNIA m.
ACUTE TEST WITH FATHEAD MINNOW
ACUTE TEST WITH CERIODAPHNIA d.
ACUTE TEST WITH DAPHNIA m.
ACUTE LOW VOLUME SCREEN
MICROTOX TEST
(Note: Cost for biomonitoring samples funded differently)
|  | SLOH Total = |  | 4473.28