Semi-Annual Report for GL-00E00466

For time period ending 10/31/2011

Barrens Habitat Restoration for Endangered/Threatened Species

I.  Restoration Work Accomplished

Table 1:  Six-month accomplishments

| Property | Project Activity | Amount completed |
| --- | --- | --- |
| Emmons Creek W.A. | Logging slash reduction | 14 acres |
| Greenwood W,.A. | Brush and tree removal | 12 acres |
| Greenwood W.A. | Prescribed burning | 18 acres |
| White River W.A. | Tree removal | 3 acres |
| Greenwood W.A. | Firebreak construction | 2 miles |
| White River W.A. | Prescribed burning | 28 acres |
| All treatment sites | Pre-management vegetation surveys | 980 acres |
| Reference sites | Karner butterfly surveys | 79 acres |
| Restoration sites | Karner butterfly surveys | 40 acres |
| Total Acres Treated |  | 75 acres |
| Total Acres Surveyed |  | 1099 acres |

This grant project involves four Wisconsin DNR properties located within the high probability range of the federally endangered Karner blue butterfly (Lycaeides melissa samuelis).  It is intended to restore and enhance over 1,300 acres of barrens habitat that supports the Karner blue and more than fifty other state and federal SGCN’s (species of greatest conservation need).

During the six month period ending October 31, 2011 the primary achievement was the collection of data establishing vegetative composition and structure on nearly 1,000 acres of sites designated for restoration.  This was a requirement of the QAPP.  In spite of a late start in the field season, the three properties noted above were able to treat 75 acres of habitat by reducing forest canopy and by conducting prescribed burning.

II.   Object Class Category Changes

None

III.  Corrective Actions

None

IV.  Projected New Work through April, 2012

Table 2:  Six-month projected work plans

| Property | Activity | Amount Planned |
| --- | --- | --- |
| Emmons Creek W.A. | Burn brush piles | 5 Acres |
|  | Tree/brush cutting and grinding | 15 Acres |
|  | Chemical stump treatment | 5 Acres |
| Hartman Creek State Park | Tree/brush cutting and grinding | 20 Acres |
|  | Prescribed burning | 40 acres |
| Greenwood W.A. | Tree/brush cutting and grinding | 25 Acres |
|  | Prescribed burning | 200 Acres |
| White River W.A. | Tree/brush cutting and grinding | 5 Acres |
|  | Prescribed burning | 150 Acres |
| Total Treatments Planned |  | 465 Acres |

V.  Percent Completion of Scheduled Work

Table 3:  Percentage of project completed to date

| Activity | Projected Acres | Target Date | Completed Acres | Percent Completed |
| --- | --- | --- | --- | --- |
| Tree/brush removal | 120 | 07/30/2012 | 26 | 21.7% |
| Invasive plant control | 132 | Not Established | 0 | 0% |
| Prescribed burn | 1253 | 06/30/2013 | 46 | 3.7% |
| Seeding | 180 | 11/30/2012 | 0 | 0% |
| Monitoring phase 1 | 1685 | 08/31/2011 | 1099 | 65.5% |

Tree and brush removal were conducted on the Emmons Creek, Greenwood and White River Wildlife Areas in the winter of 2010 – 2011 by cutting trees and using mechanized brush grinders to reduce tree tops and other woody debris.  This treatment opens up the sites for better development of native grasses and forbs by allowing more sunlight to reach the ground.  Two miles of firebreak were established on the Greenwood Wildlife Area to prepare for prescribed burning, but only one 18 acre burn was conducted due to adverse weather conditions. On White River Wildlife Area a single burn of 28 acres was conducted.  No seeding was accomplished during this reporting period due to logistical and weather problems.  However, some grass and forb mixes for barrens seeding has already been purchased and will be planted once sites have been prepared properly.

Habitat assessment was conducted on 980 acres of sites in the summer of 2011.  These sites are scheduled for a variety of treatments including herbicide control of invasive plants, prescribed burning, tree and brush removal, and seeding of barrens forbs and grasses.  In addition, Vegetation surveys and Karner blue butterfly population estimates were conducted on designated reference sites for each property participating in this restoration grant.  Karner abundance surveys were conducted on three restoration sites that support small Karner populations to track population trends for those sites.  Habitat assessment and Karner surveys were conducted by citizen volunteers, WDNR staff, USFWS staff, and the University of Wisconsin – Stevens Point.

Photos of project activities for the reporting period will be mailed to the Project Manager via CD disk due to the size of the files.

VI.   Budget Expenditures

Table 4:  Percent of Budgeted Amount Spent to date

| Amount of GLRI grant | $ 109,431 |
| --- | --- |
| Expended to date | $ 15,861 |
| Percent expended | 14.5% |

VII.   Change in Principal Investigator

No change

VIII.  Changes Needed in Project Period

This grant expires in late 2013.  Completion of restoration activities by that date may not be possible due to delays at the start of the grant period.  Also, final surveys to measure vegetative response to management will most likely require an extension to at least one year past the implementation of on-site restoration activities.

IX.   Delays or Adverse Conditions

The project is running behind schedule for several reasons

- The greatest single factor in delaying the implementation of this grant was the development of the mandatory QAPP which turned out to be far more complicated and difficult than anticipated.  It required the development of a new vegetation survey method that collects quantitative data measuring vegetative composition and structure on treatment sites.  We developed a sampling design along with sampling methods and protocols, and measuring tools for plot data collection.  Each of 31 separate sites had to be mapped and random sampling points were generated using Arc Map GIS technology.  Survey crews were trained in the summer of 2011.  It took them until late August to complete all of the sampling.  The data has only recently been processed and is now ready to share with  property managers for their work planning process.

- A separate GIS analysis tool was also developed to measure percent canopy from NAIP ortho photos.  NAIP photos are flown annually, allowing us to measure forest and brush canopy pre and post management for restoration sites.

- Weather was a contributing factor in the delay of project startup and implementation. Prescribed burning was planned on a large scale for the spring of 2011.  Burns are normally conducted in March and April, as soon as the snow has melted.  Early spring in 2011 was generally cool wet and only two small burns totaling 46 acres were possible.

- Several of the properties experienced staff shortages last summer due to Wisconsin’s economic crisis.  Most vacancies were frozen until later in the summer, by which time it was too late to make significant progress on restoration projects.