PROGRESS  REPORT 2

USEPA-Great Lakes Restoration Initiative Project

Grant or IA Number: EPAGLNPO-2010-TX-10-1058-1042

Project Title: Contaminants of Emerging Concern Product Stewardship Project

Reporting Period Covered: April 1, 2011 - September 30, 2011

Principal Investigator: Steve Brachman

1.	Accomplishments - the following is a brief summary of results to date by project task:

1. Expand the mail back collection program through out the 36 counties that are part of the WI Great Lakes watershed.

  - A contract with the University of Maine to emulate their mail back program has been in place for 9 months that includes processing and disposal of controlled substances by the Maine Drug Enforcement Agency (DEA).

  - New promotional materials included a fact sheet on pharmaceutical waste in the Great Lakes (see http://fyi.uwex.edu/pharma/files/2011/08/Additional-Fact-Sheet.pdf).

  - 317 facilities and organizations returned participant agreements and are now participating int the Get Out the Meds program.   7500 envelopes were initially distributed in lots of 25 in early August; and additional 6200 envelopes were distributed thru Sept 30 as facilities exhausted their supplies. Ongoing response from consumers has been very good with 736  pounds and 1601 envelopes returned to the Maine DEA during the first 7 weeks of this program.

  - One press release was issued in August, 2 radio and 1 television interview were conducted. Major spikes in the number of hits on our web site resulted from these outreach efforts.

  - The Wisconsin pharmaceutical waste working group received broad support from the Wisconsin State Council on Alcohol and Drug Abuse which incorporated many of the working groups recommendations in their final report. Additionally, 5 sub-groups were formed to focus on key issues.

2. Develop parallel working groups in 4 other states (MN, IL, MI, IN)

  - Working groups from the states continue to demonstrate good progress, participating in a series of regional calls/webinars as described below:

| Regional workgroup calls/webinars |
| --- |
|  | April 11, 2011 | This call focused on reviewing proposed revisions to the draft problem statement. The discussion centered on demarcating the scope of the project and whether to include issues such as the use of pharmaceuticals in agriculture, increasing incidences of prescription drug abuse, and the status of wastewater treatment facilities within the scope of the problem the group was addressing. |
|  | May 2, 2011 | This call focused on preparation for the in-person meeting hosted in Milwaukie. PSI reviewed the draft meeting agenda, speakers and breakout session topics and solicited input for the group on proposed revisions. |
|  | Monday, July 11, 2011 | This call focused on discussing the May 12th meeting and a discussion of proposed next steps for developing a regional model for pharmaceutical stewardship. On the call the group also reviewed legislative updates from Illinois, New York, Ohio, and Indiana. There was a also final review and approval of the issue statement. |
|  | August 8, 2011 | On this call PSI provided a short update on the goals for the briefing document and solicited input on which resources and recent studies should be included in addition to the preliminary list assembled by PSI. On the call there was a first discussion of the draft principles for a model program. Several specific questions were considered including the scope and goals of developing such a model. |
|  | September 12, 2011 | On this call the group discussed the next draft of these principles, and developed strategies for reaching out to other groups and agencies for building support for the project and project goals. |

Representatives from the states of Ohio and New York were not part of the original project plan; however, they have maintained broad interest and participation. The monthly calls have resulted in a draft Key Elements of Pharmaceutical Collection and Disposal Programs: A Vision for the Great Lakes Region. This short document succinctly outlines the key criteria needed to ensure a successful collection and disposal program including: sustainable funding, sustained public outreach and education efforts, waste management practices that provide maximum protection for the environment, on-going, secure, affordable, and widely accessible programs. Additionally a successful program should also focus on the addressing the underlying drivers that contribute to pharmaceutical waste to improve medical care and reduce medical costs. In addition, work has begun on developing an issue statement to explain scope of problem, regional infrastructure, and objectives of regional model.

3. Coordinate public relations and outreach

  - Implementation of a PR strategy developed in conjunction with UW-Extension media relations staff for outreach communication on the project was initiated (see item 1D above).

  - A comprehensive project website was maintained at http://fyi.uwex.edu/pharma. New features of this website include press releases, fact sheets, program updates, media interviews, as well as updated product stewardship information

  - Over fifty representatives from many of the states participated in a May 12th workshop in Milwaukee to develop and further our mutual agenda. A summary and presentations are listed at:

http://fyi.uwex.edu/pharma/resources/get-the-old-meds-out-conference-2010/.

The remaining tasks listed below will be implemented in the near future:

4. Convene multi-stakeholder product stewardship dialog with industry partnership

5. Provide biannual white papers to document state progress in collecting, stewardship initiatives, and goal achievement

- A draft white paper has been developed and will be finalized in November, 2011

6. Monitor implementation of the product stewardship strategy

- What, if any, changes were made from the Object Class Categories listed in Sec. B of the SF 424A or Box 29 of the IA, as applicable?

No changes were made to the Object Class Categories or Box 29

- If a problem was encountered, what action was taken to correct it?

  - A significant delay in the mail back program occurred when the US Postal Service established additional requirements for the State of Maine. These requirements increased costs for mailing; however, these were offset by printing savings.

- What work is projected for the new reporting period activity?

  - The mail back program will continue until the end of the grant period. PR and outreach will continue  and a targeted effort to boost participation from low income communities will be initiated. Planning will also begin for a spring dialogue/roundtable discussion. Work with state working groups will continue

- Is the project work on schedule? Yes

List activities from the Work Plan, and any required Quality System Documentation, and report as percent completed.

| Activity | % completed 4/1 - 9/30/11 | % completed project |
| --- | --- | --- |
| 1. Expand mail back | 25% | 50% |
| 2. Parallel working groups | 20% | 45% |
| 3. Public relations/outreach | 25% | 50% |
| 4. Product stewardship dialogue | 5% | 5% |
| 5.Document state progress | 15% | 15% |
| 6. Monitor implementation | 0% | 0% |

6.	Does the project funding rate support the work progress?  Yes   Report as percent spent of budgeted amounts for Federal and non-Federal.  21%

- Is there a change in principal investigator?

- No

- Will the project take longer than the approved project period?  If so, have you formally requested an amendment in writing?

- We anticipate needing an additional year to complete the product stewardship work, but are unsure at this time if sufficient funding is available.

9. 		What is the date and amount of your latest drawdown request?  If no request has been submitted, please explain.

- What is the date of your latest entry into the Great Lakes Accountability System?

- 10/13/11

Appendix